## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KHARIKA AND ITS ADJOINING MOUZAS PWSS | SM/15015 | New | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 98/MD | 10/01/2023 | 10/01/2023 | Resource Division | 18.9 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KHARIKA AND ITS ADJOINING MOUZAS PWSS | SM/15015 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHARIKA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001923/2022-2023 | 842/W/MMD | 24/03/2023 | 01/03/2025 | ORIENTAL ENGINEERING CO. | 27.35 | 0 | 0 | 30
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KHARIKA AND ITS ADJOINING MOUZAS PWSS | SM/15015 | New | Material Requisition To Resource Division |  |  | RTOR000064/2024-2025 | 3384/MD | 25/11/2024 | 25/11/2024 | Resource Division | 17.19 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KHARIKA AND ITS ADJOINING MOUZAS PWSS | SM/15015 | New | Electric quotation bill for Tw No-I of Kharika PWSS. (Ref Conumer ID-204182369) |  |  | BILL/03342/2023-2024 | BP-2023-24-563 | 16/01/2024 | 16/01/2024 | WBSEDCL | 3.2 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KHARIKA AND ITS ADJOINING MOUZAS PWSS | SM/15015 | New | Electric quotation bill for Tw No-II of KHARIKA PWSS. (Ref Consumer ID-204195441), APPLICATION NO-2004564930, APPLICATION TYPE-NEW CONNECTION,NAME OF CCC-ANANDAPUR CCC, BLOCK-KESHPUR. |  |  | BILL/03575/2023-2024 | BP-2023-24-642 | 08/02/2024 | 08/02/2024 | WBSEDCL | 4.79 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KHARIKA AND ITS ADJOINING MOUZAS PWSS | SM/15015 | New | Sinking Of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2790 Nos) under JJM with allied work for Kharika & its adjoining mouzas W/S scheme in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000068/2023-2024 | 2421/MD | 13/07/2023 | 31/03/2026 | BANERJEE CONSTRUCTION | 819.46 | 259.05 | 31.61 | 45
7 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KHARIKA AND ITS ADJOINING MOUZAS PWSS | SM/15015 | New | Laying of rising main & interconnection for Kharika & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 320 Mtr.) | AE Sadar Sub-division |  | ORD/000437/2024-2025 | 322/MD | 29/01/2025 | 15/03/2025 | MAA SARADA ENTERPRISE | 5 | 0 | 0 | 0
Total | [13 empty] | 895.9 | 259.05 | 28.91