## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | KUTKI AND ADJOINING MOUJAS PWSS | SM/15016 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KUTKI AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. (Part-II) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001956/2022-2023 | 869/W/MMD | 27/03/2023 | 23/09/2023 | JAL PRAVAHIKA PVT. LTD. | 11.95 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Narayangarh | Central Drilling | KUTKI AND ADJOINING MOUJAS PWSS | SM/15016 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 13.03 | 0.06 | 11
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | KUTKI AND ADJOINING MOUJAS PWSS | SM/15016 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE2 Kharagpur Sub Division | ORD/000212/2023-2024 | 2823/MD | 07/08/2023 | 24/03/2026 | S & P ENTERPRISE | 3925.58 | 19.42 | 0.49 | 20
4 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | KUTKI AND ADJOINING MOUJAS PWSS | SM/15016 | New | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 1176/MD | 26/04/2023 | 26/04/2023 | Resource Division | 27.09 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | KUTKI AND ADJOINING MOUJAS PWSS | SM/15016 | New | Quotation for new power connection at Kutki PWSS T/W- I ,Narayangarh Block , Application no- 2004677554 , ref. Id - 204270807 |  |  | BILL/00702/2024-2025 | BP2024-25-152 | 09/05/2024 | 09/05/2024 | WBSEDCL | 3.97 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | KUTKI AND ADJOINING MOUJAS PWSS | SM/15016 | New | Quotation for new power connection at Kutki Pwss T/W - II within Narayangarh Block Application No- 2004857382 , Ref No - 204376545 |  |  | BILL/02117/2024-2025 | BP-2024-25-628 | 02/09/2024 | 02/09/2024 | WBSEDCL | 3.96 | 0 | 0 | 0
Total | [13 empty] | 25312.32 | 32.46 | 0.13