## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15017 | New | Preparation & Submission of 2 (Two) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Kuran & its adjoining Mouzas PWSS AND (2) Kushman & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000660/2022-2023 | 1766/MD | 24/08/2022 | 23/09/2022 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.92 | 3.32 | 47.94 | 0
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15017 | New | Material Requisition To Resource Division |  |  | RTOR000055/2022-2023 | 68/MD | 09/01/2023 | 09/01/2023 | Resource Division | 15.87 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15017 | New | QUOTATION MONEY FOR KURAN WATER SCHEME , T W NO NO 2 , APLLICATION 2004345710, REFERENCE ID 204027343, BIRSINGHA CCCC WBSEDCL |  |  | BILL/00587/2023-2024 | BP-2023-24-125 | 13/07/2023 | 13/07/2023 | WBSEDCL | 0.51 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15017 | New | QUOTATION MONEY FOR KURAN WATER SCHEME , T W NO NO 1 , APLLICATION 2004345690, REFERENCE ID 204027368, BIRSINGHA CCCC WBSEDCL |  |  | BILL/00588/2023-2024 | BP-2023-24-124 | 13/07/2023 | 13/07/2023 | WBSEDCL | 0.51 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15017 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001945/2022-2023 | 831/W/MMD | 24/03/2023 | 04/09/2025 | WEST BENGAL ENGINEERING CO. | 22.63 | 15.52 | 68.59 | 80
6 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15017 | New | Material Requisition To Resource Division |  |  | RTOR000034/2024-2025 | 3361/MD | 25/11/2024 | 25/11/2024 | Resource Division | 8.6 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15017 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 200 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1396 Nos.) under JJM with allied work for Kuran PWSS in Ghatal Block including supply of all labour & materials including 2 (Two) years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000640/2022-2023 | 577/MD | 23/02/2023 | 01/01/2025 | SUJATA CONSTRUCTION | 385.35 | 253.25 | 65.72 | 32
8 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15017 | New | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001825/2023-2024 | 1684/MMSD-I | 19/12/2023 | 17/02/2024 | SUBHASIS ROY | 0.29 | 0 | 0 | 40
9 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15017 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 05/01/2025 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
Total | [13 empty] | 446.97 | 272.09 | 60.87