## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS | SM/15025 | New | Material Requisition To Resource Division |  |  | RTOR000088/2022-2023 | 197/MD | 16/01/2023 | 16/01/2023 | Resource Division | 35.4 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS | SM/15025 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Soil investigation , 250 Cum OHR (Intze type with Raft foundation) & Accommodate FHTC (1488 nos.) under JJM with allied work including 02(Two )Years Operation & Maintenance for Narasinghapur & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000073/2023-2024 | 2146/MD | 08/06/2023 | 05/12/2023 | A.J. ENTERPRISE | 425.75 | 0 | 0 | 40
3 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS | SM/15025 | New | Material Requisition To Resource Division |  |  | RTOR000077/2024-2025 | 3427/MD | 25/11/2024 | 25/11/2024 | Resource Division | 9.17 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS | SM/15025 | New | Additional Quotation for LT network connection at Narasinghapur PWSS P/H- I , application no - 100000101096 , Ref id - 860293136 |  |  | BILL/04197/2023-2024 | BP-2023-24-781 | 06/03/2024 | 06/03/2024 | WBSEDCL | 3.12 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS | SM/15025 | New | Quotation for new power connection at Narasinghapur water supply scheme T/W - I |  |  | BILL/03560/2023-2024 | BP-2023-24-620 | 07/02/2024 | 07/02/2024 | WBSEDCL | 0.51 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS | SM/15025 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001717/2022-2023 | 616/W/MMD | 20/03/2023 | 21/03/2025 | JAGANNATH ENTERPRISE | 21.58 | 0 | 0 | 40
7 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS | SM/15025 | New | Route survey & way leave permission along & across of National Highway in Narasinghapur PWSS under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000504/2024-2025 | 587/MD | 03/03/2025 | 24/03/2025 | DONA ASSOCIATES | 10.04 | 0 | 0 | 0
Total | [13 empty] | 505.57 | 0 | 0