## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | PIRRAKULI AND ADJOINING MOUJAS PWSS | SM/15028 | New | Material Requisition To Resource Division |  |  | RTOR000267/2023-2024 | 2225/MD | 15/06/2023 | 15/06/2023 | Resource Division | 26.2 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | PIRRAKULI AND ADJOINING MOUJAS PWSS | SM/15028 | New | New Service connection charges for Pirrakuli w/s scheme, t/w no.-II |  |  | BILL/01969/2023-2024 | 187/JMD | 30/03/2024 | 30/03/2024 | WBSEDCL | 7.79 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | PIRRAKULI AND ADJOINING MOUJAS PWSS | SM/15028 | New | New Service connection charges for Pirrakuli w/s scheme, t/w no.-I |  |  | BILL/01970/2023-2024 | 188/JMD | 30/03/2024 | 30/03/2024 | WBSEDCL | 9.29 | 0 | 0 | 0
Total | [13 empty] | 43.28 | 0 | 0