## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PRATAPPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15072 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PRATAPPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002019/2022-2023 | 917/W/MMD | 27/03/2023 | 23/09/2023 | SUBHASIS ROY | 12.62 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PRATAPPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15072 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (502) for Augmentation of Pratappur PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000170/2023-2024 | 2672/MD | 26/07/2023 | 01/08/2025 | DIPAK KUMAR DOLAI | 67.82 | 8.75 | 12.91 | 10
3 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PRATAPPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15072 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000133/2022-2023 | 406/MD | 07/02/2023 | 07/02/2023 | Resource Division | 3.97 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PRATAPPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15072 | Augmentation | Restoration of damaged pipeline due to irrigation works of PRATAPPUR water supply scheme within Ghatal block under Ghatal Sub-Division within Midnapore Division, PHE.Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000032/2024-2025 | 1274/AE/GSD | 28/06/2024 | 13/07/2024 | SUBHASIS DOLAI | 0.48 | 0 | 0 | 100
5 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PRATAPPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15072 | Augmentation | Drain out the overflow water through underground to nayanjali of 700 m3 OHR of PRATAPPUR water supply scheme within Ghatal Block under Ghatal Sub-Division with Midnapore Division, P.H.E.Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000072/2024-2025 | 1441/AE/GSD | 30/08/2024 | 14/09/2024 | SUBHASIS DOLAI | 0.94 | 0 | 0 | 100
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PRATAPPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15072 | Augmentation | QUOTATION MONEY FOR PRATAPUR WATER SUPPLY SCHEME, T W NO IV, AUGMENTATION, JJM WORKS, SCHEME CODE SM /15072, APPLICATION NO 2004860703, REFERENCE ID 204377555, GHATAL CCC, WBSEDCL |  |  | BILL/02990/2024-2025 | C122407522132 | 06/12/2024 | 06/12/2024 | WBSEDCL | 8.23 | 0 | 0 | 0
Total | [13 empty] | 94.04 | 8.75 | 9.31