## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/15092 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing (i) Barisha PWSS within Pingla block & (ii) Nayagram PWSS within Midnapore Sadar Block under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division,AE Sadar Sub-division |  | ORD/000497/2022-2023 | 2064/MD | 30/09/2022 | 15/10/2022 | GOBINDA MAITY | 7.34 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/15092 | Augmentation | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW III of Nayagram water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000112/2023-2024 | 423/MMSD-I | 20/04/2023 | 05/05/2023 | DEBJYOTI BASU | 4.37 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/15092 | Augmentation | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW IV of Nayagram water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I |  | ORD/000111/2023-2024 | 424/MMSD-I | 20/04/2023 | 05/05/2023 | SUJOY RANJAN BHOWMICK | 4.37 | 0 | 0 | 60
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/15092 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000186/2023-2024 | 1395/MD | 03/05/2023 | 03/05/2023 | Resource Division | 15.86 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/15092 | Augmentation | Electric quotation for Nayagram PWSS Tube Well- IV in connection Barua CCC (2004189731) |  |  | BILL/00067/2022-2023 |  | 21/02/2023 | 21/02/2023 | WBSEDCL | 0.19 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/15092 | Augmentation | Electric quotation for Nayagram PWSS Tube Well- III in connection Barua CCC |  |  | BILL/00411/2022-2023 | BP-2022-23-159 | 31/03/2023 | 31/03/2023 | WBSEDCL | 0.19 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/15092 | Augmentation | Electric quotation for Nayagram PWSS Tube Well- IV in connection Barua CCC (2004189731) |  |  | BILL/00412/2022-2023 | BP-2022-23-160 | 31/03/2023 | 31/03/2023 | WBSEDCL | 0.19 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/15092 | Augmentation | Electric quotation for Nayagram PWSS Tube Well- III in connection Barua CCC ( |  |  | BILL/00066/2022-2023 |  | 21/02/2023 | 21/02/2023 | WBSEDCL | 0.19 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/15092 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram and its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001892/2022-2023 | 791/W/MMD | 24/03/2023 | 20/09/2023 | SHOVAN KUMAR DAS | 22.79 | 0 | 0 | 68
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/15092 | Augmentation | Laying distribution pipe line, Rising main, Boundary wall & Accommodate FHTC (200 Nos.) under JJM with allied work for Augmentation of Nayagram & its adjoining mouzas W/S Scheme in Midnapore Sadar block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000178/2023-2024 | 2718/MD | 31/07/2023 | 26/01/2024 | MIDNAPUR PIPE CONCERN | 112.05 | 0 | 0 | 40
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/15092 | Augmentation | Laying distribution pipeline under JJM with allied work for Augmentation of Nayagram & its adjoining mouzas W/S Scheme in Midnapore Sadar block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000296/2023-2024 | 3966/MD | 05/10/2023 | 19/11/2023 | AJIJUR RAHAMAN MALLICK | 24.77 | 0 | 0 | 60
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/15092 | Augmentation | Accommodate FHTC (126 Nos.), Construction of Boundary wall, Switch Room under JJM with allied work for Augmentation of Nayagram & its adjoining mouzas W/S Scheme in Midnapore Sadar block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000634/2023-2024 | 5563/MD | 26/12/2023 | 24/02/2024 | MODERN CONSTRUCTION | 18.35 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/15092 | Augmentation | Construction of OHR (250 cum) & Accommodate FHTC (200 Nos.) under JJM with allied work for Augmentation of Nayagram & its adjoining mouzas W/S Scheme in Midnapore Sadar block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE/RWS Midnapore Sub Division |  | ORD/000178/2024-2025 | 3163/MD | 05/10/2024 | 03/04/2025 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 91.94 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram & its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/15092 | Augmentation | Sinking of 2 (Two) Nos. Tube well for Augmentation of Nayagram & its adjoining mouzas PWSS in Midnapore Sadar block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000115/2023-2024 | 2516/MD | 18/07/2023 | 17/08/2023 | MIDNAPUR PIPE CONCERN | 23.44 | 0 | 0 | 55
Total | [13 empty] | 326.05 | 0 | 0