## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ranjapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15118 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Ranjapur & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Ghatal) | ORD/000656/2022-2023 | 1754/MD | 24/08/2022 | 13/09/2022 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 4.93 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ranjapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15118 | New | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 1276/MD | 28/04/2023 | 28/04/2023 | Resource Division | 33.3 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ranjapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15118 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ranjapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000194/2023-2024 | 1461/W/MMD | 13/06/2023 | 10/12/2023 | TAPAN KUMAR SARKAR | 22.99 | 0 | 0 | 40
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ranjapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15118 | New | QUOTATION MONEY FOR RANJAPUR WATER SUPPLY SCHEME, T W NO 2, JJM WORKS, SCHEME CODE SM/15118, APPLICATION NO 2004816291, REFERENCE ID 204354170, BIRSHINGHA CCC, WBSEDCL |  |  | BILL/01736/2024-2025 | BP-2024-25-505 | 30/07/2024 | 30/07/2024 | WBSEDCL | 6.72 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ranjapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15118 | New | QUOTATION MONEY FOR RANJAPUR WATER SUPPLY SCHEME, T W NO 1, JJM WORKS, SCHEME CODE SM/15118, APPLICATION NO 2004816268, REFERENCE ID 204354168, BIRSHINGHA CCC, WBSEDCL |  |  | BILL/01735/2024-2025 | BP-2024-25-500 | 30/07/2024 | 30/07/2024 | WBSEDCL | 3.09 | 0 | 0 | 0
Total | [13 empty] | 71.04 | 0 | 0