## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Sagarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/15119 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sagarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001633/2022-2023 | 491/W/MMD | 20/03/2023 | 12/07/2025 | INDTECH ASSOCIATES | 23 | 0 | 0 | 85
2 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Sagarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/15119 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 350 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1,783 nos.) under JJM with allied work for Sagarpur PWSS in Daspur- I Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance Charge within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000278/2023-2024 | 3821/MD | 20/09/2023 | 13/03/2025 | KISHORE GHOSH | 559.14 | 31.57 | 5.65 | 10
3 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Sagarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/15119 | New | Material Requisition To Resource Division |  |  | RTOR000048/2022-2023 | 107/MD | 10/01/2023 | 10/01/2023 | Resource Division | 44.15 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Sagarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/15119 | New | Material Requisition To Resource Division |  |  | RTOR000018/2024-2025 | 3355/MD | 25/11/2024 | 25/11/2024 | Resource Division | 10.98 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Sagarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/15119 | New | QUOTATION MONEY FOR SAGARPUR WATER SUPPLY SCHEME, T W NO 2, JJM WORKS, SCHEME CODE SM/15119, [ NABODAY SANGHA ] APPLICATION NO 2004809587, REFERENCE ID 204352800, DASPUR CCC, WBSEDCL |  |  | BILL/01631/2024-2025 | C072443762107 | 29/07/2024 | 29/07/2024 | WBSEDCL | 9.98 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Sagarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/15119 | New | QUOTATION MONEY FOR SAGARPUR WATER SUPPLY SCHEME, T W NO I, JJM WORKS, SCHEME CODE SM/15591, APPLICATION NO 2004809605, REFERENCE ID 204352801, DASPUR CCC, WBSEDCL |  |  | BILL/01629/2024-2025 | C072443748308 | 29/07/2024 | 29/07/2024 | WBSEDCL | 10.81 | 0 | 0 | 0
Total | [13 empty] | 658.06 | 31.57 | 4.8