## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15120 | New | Preparation & Submission of 6 (Six) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Shrirampur & its adjoining Mouzas PWSS, (2) Dontiara & its adjoining Mouzas PWSS, (3) Dhashachandpur Mouza Stand Alone PWSS, (4) Udayganj (P) Mouza Stand Alone PWSS, (5) Prasadchak Mouza Stand Alone PWSS AND (6) Anandapur Mouza Stand Alone PWSS, Block - Ghatal under Midnapore Division, PHE Dte. [Name of Proposed PWSS Chaulisingpur & its adjoining Mouzas PWSS & Hemantapur & its adjoining Mouzas PWSS instead of (1) Dhashachandpur Mouza Stand Alone PWSS, (2) Udayganj (P) Mouza Stand Alone PWSS, (3) Prasadchak Mouza Stand Alone PWSS AND (4) Anandapur Mouza Stand Alone PWSS] | AE Ghatal Sub-division |  | ORD/000661/2022-2023 | 1767/MD | 24/08/2022 | 08/10/2022 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.73 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15120 | New | Material Requisition To Resource Division |  |  | RTOR000136/2022-2023 | 409/MD | 07/02/2023 | 07/02/2023 | Resource Division | 7.09 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15120 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001748/2022-2023 | 651/W/MMD | 20/03/2023 | 16/09/2023 | KAMAKSHYA ENTERPRISE | 10.77 | 0 | 0 | 80
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15120 | New | Sinking of Tube well, Laying distribution pipe line, Rising main, Pump House, Operation & maintenance of 2 years under JJM with allied work for Shrirampur PWSS in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000122/2023-2024 | 2493/MD | 17/07/2023 | 15/09/2023 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 42.45 | 0 | 0 | 60
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15120 | New | Construction of Boundary wall, Soil investigation, 100 cum OHR (Torch type with solid raft) & Accommodate FHTC (667 nos.) under JJM with allied work for Shrirampur PWSS in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000846/2023-2024 | 807/MD | 15/03/2024 | 11/09/2024 | M/S. SOURAV MAHAPATRA | 103.06 | 0 | 0 | 30
6 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15120 | New | Laying Distribution system pipe line for Shrirampur W/S Scheme under JJM within Ghatal Block under Ghatal Sub-Division under Midnapore Division, PHE Dte. (PART - 'E') | AE Ghatal Sub-division |  | ORD/000034/2024-2025 | 2262/MD | 23/07/2024 | 06/09/2024 | BHOWMIK CONSTRUCTION | 14.53 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15120 | New | Laying distribution pipe line under JJM with allied work for Shrirampur PWSS in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000049/2023-2024 | 1432/MD | 04/05/2023 | 01/01/2025 | AJITESH ACHARJEE | 14.56 | 0 | 0 | 40
8 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15120 | New | QUOTATION MONEY FOR SHRIRAMPUR WATER SUPPLY SCHEME, T W NO I JJM WORKS, SCHEME CODE SM/15120, APPLICATION NO 2004760170, REFERENCE ID 204322019, GHATAL CCC, WBSEDCL |  |  | BILL/01218/2024-2025 | BP-2024-25-294 | 18/06/2024 | 18/06/2024 | WBSEDCL | 3.63 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15120 | New | Laying distribution pipe line under JJM with allied work for Shrirampur PWSS in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Ghatal),JE1 Ghatal Sub-division | ORD/000147/2023-2024 | 2637/MD | 24/07/2023 | 01/06/2024 | HYDRO TECH ASSOCIATES | 9.71 | 0 | 0 | 90
Total | [13 empty] | 212.53 | 0 | 0