## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/15121 | New | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 102/MD | 10/01/2023 | 10/01/2023 | Resource Division | 32.36 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/15121 | New | Material Requisition To Resource Division |  |  | RTOR000164/2023-2024 | 1373/MD | 02/05/2023 | 02/05/2023 | Resource Division | 10.87 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/15121 | New | New service connection |  |  | BILL/00624/2023-2024 | 7/JMD | 11/10/2023 | 11/10/2023 | WBSEDCL | 6.36 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/15121 | New | New service connection |  |  | BILL/00623/2023-2024 | 6/JMD | 11/10/2023 | 11/10/2023 | WBSEDCL | 5.63 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER HANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/15121 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. |  |  | ORD/002037/2022-2023 | 945/W/MMD | 28/03/2023 | 24/09/2023 | DEBJYOTI BASU | 25.25 | 0 | 0 | 5
Total | [13 empty] | 80.47 | 0 | 0