## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Gholshahi mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/15220 | New | Preparation of D.P.Rs (Consultancy work) in connection with the Proposed Mini Pipe Water Supply Scheme for Mouza- (i) Gholshahi & (ii) Krishnaballavpur under Dewanchak-II Gram Panchayat of SAGY (Sanshad Adarshya Gram Yagona) within Ghatal Block under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division |  | ORD/000241/2021-2022 | 1308/MD | 12/08/2021 | 22/08/2021 | SIRCON ENGINEERING SERVICES | 3.16 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Gholshahi mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/15220 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-I under Gholshai water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000093/2023-2024 | 1299/W/MMD | 12/05/2023 | 09/09/2023 | KAMAKSHYA ENTERPRISE | 5.93 | 0 | 0 | 80
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Gholshahi mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/15220 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Gholshahi (Zone-II), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000639/2022-2023 | 557/MD | 22/02/2023 | 01/06/2024 | KISHORE GHOSH | 41.91 | 0 | 0 | 50
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Gholshahi mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/15220 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Gholshahi (Zone-I), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000638/2022-2023 | 556/MD | 22/02/2023 | 01/06/2024 | KISHORE GHOSH | 45.54 | 0 | 0 | 70
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Gholshahi mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/15220 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-II under Gholshai water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000094/2023-2024 | 1300/W/MMD | 12/05/2023 | 09/09/2023 | SUBHRA ENTERPRISE | 5.91 | 0 | 0 | 100
6 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Gholshahi mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/15220 | New | Material Requisition To Resource Division |  |  | RTOR000043/2024-2025 | 3352/MD | 25/11/2024 | 25/11/2024 | Resource Division | 2.41 | 0 | 0 | 0
Total | [13 empty] | 104.87 | 0 | 0