## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15257 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 350 Cum RCC Over Head Reservoir (Intze type with solid raft) & Accommodate FHTC (1976 Nos.) including Two years O&M under JJM with allied work for Raghunathpur & its adjoining mouzas W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000128/2023-2024 | 2526/MD | 18/07/2023 | 14/01/2024 | ANIRUDDHA BAG | 582.89 | 561.48 | 96.33 | 96
2 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15257 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist-Paschim Medinipurunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002196/2022-2023 | 450/W/MMD | 20/03/2023 | 03/11/2025 | J K ENGINEERING CO | 22.94 | 14.1 | 61.46 | 100
3 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15257 | New | Material Requisition To Resource Division |  |  | RTOR000093/2022-2023 | 190/MD | 16/01/2023 | 16/01/2023 | Resource Division | 13.79 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15257 | New | QUOTATION FOR NEW POWER CONNECTION OF RAGHUNATHPUR [ BONPATNA-I] WATER SUPPLY ASCHEME [ APPLICATION --2004479616, REFERENCE ID ----204122242, NIMPURA CCC, QUOTATION NO ---2004479616/QUOT/03 DATED 26/10/2023, SCHEME NAME --- RAGHUNATHPUR [ BONPATNA -I] . , SCHEME CODE ---SM/15257 , MB NO--3580 ] |  |  | BILL/02918/2023-2024 | BP-2023-24-349 | 10/11/2023 | 10/11/2023 | WBSEDCL | 3.73 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15257 | New | QUOTATION FOR NEW POWER CONNECTION OF RAGHUNATHPUR [ BONPATNA-II] WATER SUPPLY ASCHEME [ APPLICATION --2004479629, REFERENCE ID ----204122243, NIMPURA CCC, QUOTATION NO ---2004479629/QUOT/03 DATED 26/10/2023, SCHEME NAME --- RAGHUNATHPUR [ BONPATNA -II] . , SCHEME CODE ---SM/15257 , MB NO--3580 ] |  |  | BILL/02919/2023-2024 | BP-2023-24-348 | 10/11/2023 | 10/11/2023 | WBSEDCL | 3.64 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15257 | New | Material Requisition To Resource Division |  |  | RTOR000078/2024-2025 | 3429/MD | 25/11/2024 | 25/11/2024 | Resource Division | 12.17 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15257 | New | Laying balance distribution system to accommodate FHTC (350 Nos.) for Raghunathpur & its adjoining mouzas W/S Scheme, Block - Kharagpur-I, District - Paschim Medinipur under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000879/2024-2025 | 206/MD | 17/01/2025 | 02/04/2025 | ANIRUDDHA BAG | 56.29 | 0 | 0 | 0
Total | [13 empty] | 695.46 | 575.58 | 82.76