## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Maharajpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15325 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Maharajpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001611/2022-2023 | 493/W/MMD | 20/03/2023 | 16/09/2023 | S.P. ENTERPRISE | 22.95 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Maharajpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15325 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Maharajpur & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Ghatal) | ORD/000654/2022-2023 | 1752/MD | 24/08/2022 | 13/09/2022 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 4.95 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Maharajpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15325 | New | Material Requisition To Resource Division |  |  | RTOR000054/2022-2023 | 60/MD | 09/01/2023 | 09/01/2023 | Resource Division | 36.92 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Maharajpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15325 | New | Material Requisition To Resource Division |  |  | RTOR000036/2024-2025 | 3363/MD | 25/11/2024 | 25/11/2024 | Resource Division | 13.44 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Maharajpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15325 | New | QUOTATION MONEY FOR MAHARJPUR WATER SUPPLY SCHEME, T W NO I, JJM WORKS, SCHEME CODE SM/15325, APPLICATION NO 2004857637, REFERENCE ID 204376542, BIRSINGHA CCC, WBSEDCL |  |  | BILL/03034/2024-2025 | C112429741036 | 25/11/2024 | 25/11/2024 | WBSEDCL | 3.31 | 0 | 0 | 0
Total | [13 empty] | 81.58 | 0 | 0