## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | BHATUIGERYA PIPED WATER SUPPLY SCHEME | SM/15509 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BHATUIGERYA PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001642/2022-2023 | 574/W/MMD | 20/03/2023 | 16/09/2023 | DEY ENTERPRISE | 25.26 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | BHATUIGERYA PIPED WATER SUPPLY SCHEME | SM/15509 | New | Material Requisition To Resource Division |  |  | RTOR000193/2023-2024 | 1406/MD | 04/05/2023 | 04/05/2023 | Resource Division | 57.13 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | BHATUIGERYA PIPED WATER SUPPLY SCHEME | SM/15509 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of BHATUIGERIA PWSS. REF CONSUMER ID-204269804, APPLICATION NO-2004675318, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/00309/2024-2025 | BP-2024-25-78 | 24/04/2024 | 24/04/2024 | WBSEDCL | 4.27 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | BHATUIGERYA PIPED WATER SUPPLY SCHEME | SM/15509 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of BHATUIGERIA PWSS. REF CONSUMER ID-204269077, APPLICATION NO-2004675295, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/00315/2024-2025 | BP-2024-25-79 | 24/04/2024 | 24/04/2024 | WBSEDCL | 3.82 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | BHATUIGERYA PIPED WATER SUPPLY SCHEME | SM/15509 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 450 (Intze type with Pile Foundation) & Accommodate FHTC (2,554 Nos.) including Two years O&M under JJM with allied work for Bhatuigerya & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000263/2023-2024 | 3237/MD | 11/09/2023 | 23/03/2026 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 837.38 | 0 | 0 | 37
Total | [13 empty] | 927.86 | 0 | 0