## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15533 | New | Material Requisition To Resource Division |  |  | RTOR000103/2022-2023 | 180/MD | 16/01/2023 | 16/01/2023 | Resource Division | 36.49 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15533 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001621/2022-2023 | 536/W/MMD | 20/03/2023 | 16/09/2023 | AHALYA ENGINEERING WORKS | 45.54 | 29.36 | 64.46 | 60
3 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15533 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. (Part-II) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001958/2022-2023 | 870/W/MMD | 27/03/2023 | 23/09/2023 | AHALYA ENGINEERING WORKS | 35.94 | 22.11 | 61.52 | 35
4 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15533 | New | Material Requisition To Resource Division |  |  | RTOR000079/2024-2025 | 3430/MD | 25/11/2024 | 25/11/2024 | Resource Division | 29.45 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15533 | New | QUOTATION MONEY FOR ARJUNI WATER SUPPLY SCHEME, ZONE-I, T W NO I , [ RADHANAGAR ] , JJM WORKS, SCHEME CODE SM/15533, APPLICATION NO 2004722207, REFERENCE ID 204303570, NIMPURA CCC, WBSEDCL |  |  | BILL/01464/2024-2025 | BP-2024-25-426 | 16/07/2024 | 16/07/2024 | WBSEDCL | 3.24 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15533 | New | QUOTATION MONEY FOR ARJUNI WATER SUPPLY SCHEME, ZONE-II, T W NO I, [ BALARAMPUR ] , JJM WORKS, SCHEME CODE SM/15533, APPLICATION NO 2004734869, REFERENCE ID 204308441, NIMPURA CCC, WBSEDCL |  |  | BILL/01734/2024-2025 | BP-2024-25-503 | 30/07/2024 | 30/07/2024 | WBSEDCL | 7.56 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15533 | New | QUOTATION MONEY FOR ARJUNI WATER SUPPLY SCHEME, ZONE IV , T W NO I , MINI , JJM WORKS, SCHEME CODE SM/15533, APPLICATION NO 2004601377, REFERENCE ID 204217215, MANIKPARA CCC, WBSEDCL |  |  | BILL/04208/2023-2024 | BP-2023-24-789 | 06/03/2024 | 06/03/2024 | WBSEDCL | 0.11 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15533 | New | QUOTATION MONEY FOR ARJUNI WATER SUPPLY SCHEME, ZONE-II, T W NO 2, [PATHRI ], JJM WORKS, BLOCK- KHARAGPUR-I, SCHEME CODE SM/15533, APPLICATION NO 2004834083, REFERENCE ID 204364748, NIMPURA CCC, WBSEDCL |  |  | BILL/02041/2024-2025 | BP-2024-25-602 | 29/08/2024 | 29/08/2024 | WBSEDCL | 4.53 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15533 | New | ARJUNI WATER SUPPLY SCHEME, ZONE- III, T W - I ,[ SHUSHNIA ] , JJM WORKS, SCHEME CODE SM/15533, APPLICATION NO 2004614503, REFERENCE ID 204224894, NIMPURA CCC, WBSEDCL |  |  | BILL/04209/2023-2024 | BP-2023-24-788 | 06/03/2024 | 06/03/2024 | WBSEDCL | 0.11 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15533 | New | QUOTATION MONEY FOR ARJUNI , ZONE-III, TW-I, WATER SUPPLY SCHEME, T W NO I , JJM WORKS, SCHEME CODE SM/15533, APPLICATION NO 2004793768, REFERENCE ID 204340976, NIMPURA CCC, WBSEDCL |  |  | BILL/01461/2024-2025 | BP-2024-25-425 | 16/07/2024 | 16/07/2024 | WBSEDCL | 0.11 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15533 | New | QUOTATION MONEY FOR ARJUNI WATER SUPPLY SCHEME, Z-V, T W NO I , [ HARIHARPUR ] , JJM WORKS, SCHEME CODE SM/15533, APPLICATION NO 2004800012, REFERENCE ID 204344344, NIMPURA CCC, WBSEDCL |  |  | BILL/02359/2024-2025 | C092403086596 | 04/09/2024 | 04/09/2024 | WBSEDCL | 1.52 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15533 | New | Sinking of Tube Wells, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 250 cum & 350 cum OHRs & Accommodate FHTC (4,781 Nos.) including Two years O&M under JJM with allied work for Arjuni (Zone-I,II,III IV,V&VI) & its adjoining mouzas W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000272/2023-2024 | 3259/MD | 12/09/2023 | 28/02/2026 | MAHAVIR PUMPS MFG. PVT. LTD. | 1337.7 | 305.65 | 22.85 | 35
13 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15533 | New | Hiring of Bharat Stage IV/V diesel Motor Cabs usury AC), having contract Carriage permit from the Regional Transport Authority for the offies of the Assistant Engineer, Kharagpur Sub-Division, PILE. Die. (For 06 months). period for 23.03.2024 to 22.09.2024 | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division,JE3 Kharagpur Sub-division | ORD/000934/2023-2024 | 1598/AE/KSD | 22/03/2024 | 18/09/2024 | M/S. SOMNATH | 1.01 | 1.52 | 150.73 | 0
Total | [13 empty] | 1503.3 | 358.63 | 23.86