## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. | SM/15567 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Ghatal block under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division |  | ORD/000736/2022-2023 | 2683/MD | 30/12/2022 | 20/01/2023 | RISHAN ENGINEERING CONSULTANCY | 7.72 | 2.08 | 26.95 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. | SM/15567 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Daspur-I block under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division |  | ORD/000735/2022-2023 | 2682/MD | 30/12/2022 | 20/01/2023 | RISHAN ENGINEERING CONSULTANCY | 7.76 | 2.12 | 27.25 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. | SM/15567 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002020/2022-2023 | 918/W/MMD | 27/03/2023 | 23/09/2023 | MAA TARA ENTERPRISE | 25.2 | 9.61 | 38.14 | 85
4 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. | SM/15567 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (325) for Augmentation of Ranapur PWSS in Daspur-I block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000198/2023-2024 | 2812/MD | 07/08/2023 | 24/08/2024 | KISHORE GHOSH | 82.99 | 39.15 | 47.17 | 70
5 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. | SM/15567 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000134/2022-2023 | 407/MD | 07/02/2023 | 07/02/2023 | Resource Division | 3.42 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. | SM/15567 | Augmentation | QUOTATION MONEY FOR RANAPUR WATER SUPPLY SCHEME, T W NO III [ BAIDYAPUR ] , JJM WORKS, SCHEME CODE SM/15567, [ PARENT CODE - SM/04578 ] APPLICATION NO 2004648343, REFERENCE ID 204250593, DASPUR CCC, WBSEDCL |  |  | BILL/00308/2024-2025 | BP-2024-25-70 | 24/04/2024 | 24/04/2024 | WBSEDCL | 10.58 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. | SM/15567 | Augmentation | QUOTATION MONEY FOR RANAPUR WATER SUPPLY SCHEME, T W - III , JJM WORKS, SCHEME CODE SM/15567, APPLICATION NO 2004697947, REFERENCE ID 204284912, DASPUR CCC, WBSEDCL |  |  | BILL/00640/2024-2025 |  | 29/04/2024 | 29/04/2024 | WBSEDCL | 3.09 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK INPASCHIM MIDNAPORE DISTRICT UNDER MIDNAPOREDIVISION, PHE DTE. | SM/15567 | Augmentation | QUOTATION MONEY FOR RANAPUR WATER SUPPLY SCHEME, T W - III , JJM WORKS, SCHEME CODE SM/15567, APPLICATION NO 2004697947, REFERENCE ID 204284912, DASPUR CCC, WBSEDCL |  |  | BILL/00641/2024-2025 | BP-2024-25-117 | 06/05/2024 | 06/05/2024 | WBSEDCL | 3.09 | 0 | 0 | 0
Total | [13 empty] | 143.84 | 52.95 | 36.81