## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-IBLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | SM/15569 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 2 Nos. PWSS within Ghatal & Chandrakona-I blocks under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division |  | ORD/000737/2022-2023 | 2684/MD | 30/12/2022 | 20/01/2023 | SIRCON ENGINEERING SERVICES | 8.23 | 2.08 | 25.31 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-IBLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | SM/15569 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. |  |  | ORD/002021/2022-2023 | 919/W/MMD | 27/03/2023 | 23/09/2023 | SUJOY RANJAN BHOWMICK | 25.26 | 21.86 | 86.52 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-IBLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | SM/15569 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (2835 Nos.) under JJM with allied work for Augmentation of Srinagar Pipe W/S Scheme in Chandrakona-I Block including supply of all labour & materials within Ghtaal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000181/2023-2024 | 2721/MD | 31/07/2023 | 22/09/2026 | M/S. D.K.H.CONSTRUCTION | 239.56 | 74.42 | 31.07 | 11
4 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-IBLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | SM/15569 | Augmentation | Damaged UPVC pipeline & withdrawing of CI PIPE and replace with DI pipe & allied works in Srinagar W/S Scheme under Ghatal Sub-Division PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000379/2023-2024 | 4041/MD | 11/10/2023 | 26/10/2023 | SAYEEDI CONSTRUCTION | 2.12 | 0 | 0 | 100
5 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-IBLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | SM/15569 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000199/2023-2024 | 1420/MD | 04/05/2023 | 04/05/2023 | Resource Division | 18.38 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-IBLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | SM/15569 | Augmentation | Restoration of pipe line for water supply arrangement due to damage of pipe line by PWD road activities of SRINAGAR water supply scheme at CK-I block within Ghatal Sub Division under Midnapore Division,P.H.E. Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000031/2024-2025 | 1273/AE/GSD | 28/06/2024 | 18/07/2024 | S.K. CONSTRUCTION (SONDIP BANERJEE) | 0.96 | 0 | 0 | 100
7 | PASCHIM MEDINIPUR |  | Jhargram Mechanical Division | AUGMENTATION OF GROUND WATER BASED PIPED WATERSUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTCUNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-IBLOCK IN PASCHIM MIDNAPORE DISTRICT UNDERMIDNAPORE DIVISION, PHE DTE | SM/15569 | Augmentation | New Service connection charges. |  |  | BILL/01281/2023-2024 | 52/JMD | 06/02/2024 | 06/02/2024 | WBSEDCL | 3.22 | 0 | 0 | 0
Total | [13 empty] | 297.73 | 98.36 | 33.04