## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15572 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Ghatal block under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division |  | ORD/000736/2022-2023 | 2683/MD | 30/12/2022 | 20/01/2023 | RISHAN ENGINEERING CONSULTANCY | 7.72 | 2.08 | 26.95 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15572 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Daspur-I block under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division |  | ORD/000735/2022-2023 | 2682/MD | 30/12/2022 | 20/01/2023 | RISHAN ENGINEERING CONSULTANCY | 7.76 | 2.12 | 27.25 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15572 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (280 Nos.) under JJM with allied work for Augmentation of Bacchra Kundu Pipe W/S Scheme in Daspur-I Block including supply of all labour & materials within Ghtaal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000136/2023-2024 | 2620/MD | 24/07/2023 | 22/09/2023 | ASHOK BANERJEE | 52.8 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15572 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000196/2023-2024 | 1418/MD | 04/05/2023 | 04/05/2023 | Resource Division | 2.93 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15572 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002016/2022-2023 | 914/W/MMD | 27/03/2023 | 26/09/2024 | GLACIER ENGINEERING CO. | 25.26 | 17.68 | 69.97 | 60
6 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15572 | Augmentation | Laying additional pipeline to provide balance FHTC under JJM in Bachhrakundu PWSS under Ghatal Sub-Division of Midnapore Division, PHE Dte. in the district of Paschim Medinipur. | AE Ghatal Sub-division |  | ORD/000038/2024-2025 | 2218/MD | 19/07/2024 | 02/09/2024 | ASHOK BANERJEE | 28.06 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15572 | Augmentation | QUOTATION MONEY FOR BACHRA KUNDU WATER SUPPLY SCHEME, T W NO4, [ AUGMENTATION ] , JJM WORKS, BLOCK- DASPUR-I, SCHEME CODE SM/15572, APPLICATION NO 2004849416, REFERENCE ID 204373204, DASPUR CCC, WBSEDCL |  |  | BILL/02046/2024-2025 | C082441572310 | 29/08/2024 | 29/08/2024 | WBSEDCL | 3.66 | 0 | 0 | 0
Total | [13 empty] | 128.18 | 21.87 | 17.06