## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARMMA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/15576 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000197/2023-2024 | 1417/MD | 04/05/2023 | 04/05/2023 | Resource Division | 29.1 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARMMA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/15576 | Augmentation | Laying distribution pipe line, Rising Main, Boundary wall, Soil investigation, 350 CuM OHR (Intze type with pile foundation) & Accommodate FHTC (264 Nos.) under JJM with allied work for Augmentation of Dharma Pipe W/S Scheme in Daspur-I Block including supply of all labour & materials within Ghtaal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000542/2024-2025 | 734/MD | 18/03/2025 | 14/09/2025 | KHAN ENTERPRISE (PARTNER - MD. BABAR ALI KHAN & MD. SHAIN KHAN) | 324.3 | 0 | 0 | 0
Total | [13 empty] | 353.41 | 0 | 0