## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | DOSATINA AND ITS ADJOINING MOUZAS PWSS | SM/15589 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 400 Cum (Intze type with Pile Foundation) & Accommodate FHTC (3,208 Nos.) including Two years O&M under JJM with allied work for Dosatina & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000230/2023-2024 | 2954/MD | 17/08/2023 | 27/12/2025 | M/S. D.K.H.CONSTRUCTION | 822.63 | 492.5 | 59.87 | 51
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | DOSATINA AND ITS ADJOINING MOUZAS PWSS | SM/15589 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DOSATINA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002009/2022-2023 | 908/W/MMD | 27/03/2023 | 21/01/2025 | SUJOY RANJAN BHOWMICK | 27.37 | 20.83 | 76.1 | 15
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | DOSATINA AND ITS ADJOINING MOUZAS PWSS | SM/15589 | New | Material Requisition To Resource Division |  |  | RTOR000192/2023-2024 | 1405/MD | 04/05/2023 | 04/05/2023 | Resource Division | 35.42 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | DOSATINA AND ITS ADJOINING MOUZAS PWSS | SM/15589 | New | Electric quotation bill for Tw No-II of Dosatina PWSS.(Ref Consumer ID-204182357) |  |  | BILL/03338/2023-2024 | BP-2023-24-555 | 16/01/2024 | 16/01/2024 | WBSEDCL | 5.43 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | DOSATINA AND ITS ADJOINING MOUZAS PWSS | SM/15589 | New | Electric quotation bill for Tw No-I of Dosatina PWSS.(ref Consumer ID-204182345) |  |  | BILL/03337/2023-2024 | BP-2023-24-554 | 16/01/2024 | 16/01/2024 | WBSEDCL | 3.93 | 0 | 0 | 0
Total | [13 empty] | 894.78 | 513.33 | 57.37