## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15590 | New | KHEMASOLI WATER SUPPLY SCHEME , TUBE WELL NO II, SCHEME CODE - SM/15590, BLOCK KHARAGPUR - I, MB NO 3580, PAGE 30-31, and ORIGINAL QUOTATION |  |  | BILL/02668/2023-2024 | BP-2023-24-261 | 26/09/2023 | 26/09/2023 | WBSEDCL | 0.54 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15590 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II and III) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002022/2022-2023 | 920/W/MMD | 27/03/2023 | 23/09/2023 | ORIENTAL ENGINEERING CO. | 31.54 | 0 | 0 | 43
3 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15590 | New | Sinking of Tube well, Laying distribution pipe line with Rising main, Switch Room (3750 X 2550) along with PVC water storage OHR having capacity 20.00 Cum & St. Ht. 8.50 Mtr. erected over roof of Switch Room by M.S. fabricated structure, FHTC (261 Nos.) & Two years O & M under JJM with allied work for Khemasoli & its adjoining mouzas W/S Scheme (Zone-III) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Sabang),JE3 Kharagpur Sub-division | ORD/000024/2023-2024 | 946/MD | 05/04/2023 | 30/12/2025 | GOUTAM PARIA | 55.7 | 0 | 0 | 95
4 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15590 | New | Sinking of Tube well, Laying distribution pipe line with Rising main, Switch Room (3750 X 2550) along with PVC water storage OHR having capacity 20.00 Cum & St. Ht. 8.50 Mtr. erected over roof of Switch Room by M.S. fabricated structure, FHTC (121 Nos.) & Two years O & M under JJM with allied work for Khemasoli & its adjoining mouzas W/S Scheme (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000855/2023-2024 | 832/MD | 15/03/2024 | 14/05/2024 | RITESH AGARWALL | 41.32 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15590 | New | Material Requisition To Resource Division |  |  | RTOR000080/2024-2025 | 3431/MD | 25/11/2024 | 25/11/2024 | Resource Division | 4.18 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15590 | New | QUOTATION MONEY FOR KHEMASOLI WATER SUPPLY SCHEME, ZONE-I, T W NO I, [ KEMASOLI], JJM WORKS, SCHEME CODE SM/15590, APPLICATION NO 2004825735, REFERENCE ID 204360220, NIMPURA CCC, WBSEDCL |  |  | BILL/00388/2024-2025 | BP-2024-25-294 | 27/08/2024 | 27/08/2024 | WBSEDCL | 3.1 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15590 | New | Sinking of Tube well, Laying distribution pipe line with Rising main, Switch Room (3750 X 2550) along with PVC water storage OHR having capacity 20.00 Cum & St. Ht. 8.50 Mtr. erected over roof of Switch Room by M.S. fabricated structure, FHTC (281 Nos.) & Two years O & M under JJM with allied work for Khemasoli & its adjoining mouzas W/S Scheme (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE3 Kharagpur Sub-division | ORD/000002/2024-2025 | 1797/MD | 07/06/2024 | 04/04/2025 | A K SIKDAR | 60.48 | 0 | 0 | 57
Total | [13 empty] | 196.86 | 0 | 0