## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Risa & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15591 | New | Material Requisition To Resource Division |  |  | RTOR000051/2022-2023 | 67/MD | 09/01/2023 | 09/01/2023 | Resource Division | 36.02 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Risa & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15591 | New | Material Requisition To Resource Division |  |  | RTOR000081/2024-2025 | 3432/MD | 25/11/2024 | 25/11/2024 | Resource Division | 13.47 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Risa & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15591 | New | QUOTATION MONEY FOR RISA WATER SUPPLY SCHEME, T W NO 2, JJM WORKS, SCHEME CODE SM/15591, APPLICATION NO 2004636219, REFERENCE ID 204240939, NIMPURA CCC, WBSEDCL |  |  | BILL/01465/2024-2025 | BP-2024-25-427 | 16/07/2024 | 16/07/2024 | WBSEDCL | 4.64 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Risa & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15591 | New | QUOTATION MONEY FOR RISA WATER SUPPLY SCHEME, T W NO I JJM WORKS, SCHEME CODE SM/15591, APPLICATION NO 2004582784, REFERENCE ID 204211198, NIMPURA CCC, WBSEDCL |  |  | BILL/03724/2023-2024 | BP-2023-24-696 | 16/02/2024 | 16/02/2024 | WBSEDCL | 3.29 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Risa & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15591 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Risa & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002012/2022-2023 | 910/W/MMD | 27/03/2023 | 06/09/2025 | JAL PRAVAHIKA PVT. LTD. | 25.24 | 15.78 | 62.53 | 95
6 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Risa & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/15591 | New | Sinking of Tube Well, Laying distribution pipe line, Rising main, Pump House, Boundary wall, Soil investigation, Construction of 450 (Intze type with pile foundation) & 250 & 400 cum OHRs (Intze type with solid raft) & Accommodate FHTC (6,370 Nos.) including Two years O&M under JJM with allied work for (1) Gokulpur (Zone-I,II & III ) and (2) Risa & its adjoining mouzas W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000094/2023-2024 | 2466/MD | 14/07/2023 | 30/09/2025 | GOBINDA MAITY | 1715.83 | 375.63 | 21.89 | 30
Total | [13 empty] | 1798.49 | 391.42 | 21.76