## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | HATKATA AND ITS ADJOINING MOUZAS PWSS | SM/15592 | New | Material Requisition To Resource Division |  |  | RTOR000194/2023-2024 | 1407/MD | 04/05/2023 | 04/05/2023 | Resource Division | 68.4 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | HATKATA AND ITS ADJOINING MOUZAS PWSS | SM/15592 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for HATKATA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002007/2022-2023 | 906/W/MMD | 27/03/2023 | 15/03/2025 | JYOTY SOLAR POWER | 27.36 | 0 | 0 | 30
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | HATKATA AND ITS ADJOINING MOUZAS PWSS | SM/15592 | New | ADDITIONAL QUOTATION FEE FOR EFFECTING NSC AT HATKATA PWSS. REF ID-860299035, APPLICATION ID-100000106465, APPLICATION TYPE-DEPOSIT WORKS OTHER THAN SERVICE CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/00688/2024-2025 | BP-2024-25-127 | 06/05/2024 | 06/05/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | HATKATA AND ITS ADJOINING MOUZAS PWSS | SM/15592 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF HATKATA PWSS. REF CONSUMER ID-204325523, APPLICATION NO-2004767096, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/01212/2024-2025 | BP-2024-25-293 | 18/06/2024 | 18/06/2024 | WBSEDCL | 5.49 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | HATKATA AND ITS ADJOINING MOUZAS PWSS | SM/15592 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of HATKATA PWSS. REF CONSUMER ID-204210559, APPLICATION NO-2004589087, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/03736/2023-2024 | BP-2023-24-699 | 16/02/2024 | 16/02/2024 | WBSEDCL | 6.35 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | HATKATA AND ITS ADJOINING MOUZAS PWSS | SM/15592 | New | ADDITIONAL QUOTATION FOR EFFECTING NSC IRO ASSISTANT ENGINEER PHE DTE FOR EFFECTING NSC IN REVISED ROUTE AT TW-I OF HATKATA PWSS, REFERENCE ID-860305080, APPLICATION ID-100000112900. APPLICATION TYPE- DEPOSIT WORKS OTHER THAN SERVICE CONNECTION. |  |  | BILL/01733/2024-2025 | C072445050786 | 30/07/2024 | 30/07/2024 | WBSEDCL | 2.46 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | HATKATA AND ITS ADJOINING MOUZAS PWSS | SM/15592 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 400 Cum OHR (Intze type with Pile Foundation) & Accommodate FHTC (2,882 Nos.) including Two years O&M under JJM with allied work for Hatkata & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000231/2023-2024 | 2955/MD | 17/08/2023 | 05/02/2026 | M/S. D.K.H.CONSTRUCTION | 719.89 | 0 | 0 | 25
Total | [13 empty] | 829.96 | 0 | 0