## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | MARKHA AND ITS ADJOINING MOUZAS PWSS | SM/15593 | New | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 1165/MD | 26/04/2023 | 26/04/2023 | Resource Division | 107.5 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | MARKHA AND ITS ADJOINING MOUZAS PWSS | SM/15593 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF MARKHA PWSS. REF CONSUMER ID-204383573, APPLICATION NO-2004868760, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR. |  |  | BILL/02130/2024-2025 | C082449441995 | 02/09/2024 | 02/09/2024 | WBSEDCL | 6.9 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | MARKHA AND ITS ADJOINING MOUZAS PWSS | SM/15593 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of MARKHA PWSS. REF CONSUMER ID-204291858, APPLICATION NO-2004701565, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/00696/2024-2025 | BP-2024-25-145 | 09/05/2024 | 09/05/2024 | WBSEDCL | 3.18 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | MARKHA AND ITS ADJOINING MOUZAS PWSS | SM/15593 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MARKHA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002010/2022-2023 | 909/W/MMD | 27/03/2023 | 01/10/2025 | ORIENTAL ENGINEERING CO. | 27.37 | 0 | 0 | 30
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | MARKHA AND ITS ADJOINING MOUZAS PWSS | SM/15593 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 500 cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,033 nos.) under JJM with allied work including 02 (Two) years Operation & Maintenance for Markha PWSS in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000223/2023-2024 | 2923/MD | 16/08/2023 | 29/05/2026 | DULAL CHANDRA DAS | 812.19 | 196.33 | 24.17 | 47
Total | [13 empty] | 957.14 | 196.33 | 20.51