## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | TEGHARI AND ITS ADJOINING MOUZAS PWSS | SM/15594 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for TEGHARI AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002008/2022-2023 | 907/W/MMD | 27/03/2023 | 23/09/2023 | JYOTY SOLAR POWER | 21.98 | 13.99 | 63.67 | 30
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | TEGHARI AND ITS ADJOINING MOUZAS PWSS | SM/15594 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 300 Cum & 400 Cum RCC Over Head Reservoir (Intze type with Pile Foundation) & Accommodate FHTC (4,797 Nos.) including Two years O&M under JJM with allied work for Teghari & Thaur & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000224/2023-2024 | 2924/MD | 16/08/2023 | 29/05/2026 | M/S. A.R. ENTERPRISE. | 1490.96 | 99.23 | 6.66 | 49
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | TEGHARI AND ITS ADJOINING MOUZAS PWSS | SM/15594 | New | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1167/MD | 26/04/2023 | 26/04/2023 | Resource Division | 6.66 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | TEGHARI AND ITS ADJOINING MOUZAS PWSS | SM/15594 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002834/2023-2024 | 339/MMSD-I | 05/03/2024 | 05/01/2025 | M/S BIKASH DE | 6.3 | 0.14 | 2.17 | 50
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | TEGHARI AND ITS ADJOINING MOUZAS PWSS | SM/15594 | New | Continuation work order for Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. (Vehicle No. WB 33 C 6546) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002164/2024-2025 | 1826/MMSD-I | 30/12/2024 | 29/06/2025 | M/S BIKASH DE | 3.69 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | TEGHARI AND ITS ADJOINING MOUZAS PWSS | SM/15594 | New | Material Requisition To Resource Division |  |  | RTOR000065/2024-2025 | 3385/MD | 25/11/2024 | 25/11/2024 | Resource Division | 12.62 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | TEGHARI AND ITS ADJOINING MOUZAS PWSS | SM/15594 | New | ADDITIONAL QUOTATION FEE FOR EFFECTING NSC AT TW-I & II of TEGHORI PWSS. REF ID-860299039, APPLICATION ID-100000106469, APPLICATION TYPE-DEPOSIT WORKS OTHER THAN SERVICE CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/00689/2024-2025 | BP-2024-25-126 | 06/05/2024 | 06/05/2024 | WBSEDCL | 0.24 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | TEGHARI AND ITS ADJOINING MOUZAS PWSS | SM/15594 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of TAGHORI PWSS. REF CONSUMER ID-204211957, APPLICATION NO-2004590158, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/03740/2023-2024 | BP-2023-24-690 | 16/02/2024 | 16/02/2024 | WBSEDCL | 8.97 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | TEGHARI AND ITS ADJOINING MOUZAS PWSS | SM/15594 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of TAGHORI PWSS. REF CONSUMER ID-204212284, APPLICATION NO-2004590144, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/03741/2023-2024 | BP-2023-24-689 | 16/02/2024 | 16/02/2024 | WBSEDCL | 0.29 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | TEGHARI AND ITS ADJOINING MOUZAS PWSS | SM/15594 | New | ADDITIONAL QUOTATION (2) FEE FOR EFFECTING NSC AT TW-I & II of TEGHORI PWSS. REF ID-860298907, APPLICATION ID-100000106407, APPLICATION TYPE-DEPOSIT WORKS OTHER THAN SERVICE CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/00690/2024-2025 | BP-2024-25-125 | 06/05/2024 | 06/05/2024 | WBSEDCL | 1.49 | 0 | 0 | 0
Total | [13 empty] | 1553.21 | 113.36 | 7.3