## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15905 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Ghatal block under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division |  | ORD/000736/2022-2023 | 2683/MD | 30/12/2022 | 20/01/2023 | RISHAN ENGINEERING CONSULTANCY | 7.72 | 2.08 | 26.95 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15905 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Daspur-I block under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division |  | ORD/000735/2022-2023 | 2682/MD | 30/12/2022 | 20/01/2023 | RISHAN ENGINEERING CONSULTANCY | 7.76 | 2.12 | 27.25 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15905 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000138/2022-2023 | 413/MD | 07/02/2023 | 07/02/2023 | Resource Division | 6.69 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15905 | Augmentation | SUPAPURSURI WATER SUPPLY SCHEME, T W - III , JJM WORKS, SCHEME CODE SM/15905, APPLICATION NO 2004588382, REFERENCE ID 204209925, DASPUR CCC, WBSEDCL |  |  | BILL/04200/2023-2024 | BP-2023-24-787 | 06/03/2024 | 06/03/2024 | WBSEDCL | 3.08 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15905 | Augmentation | QUOTATION MONEY FOR SUPAPURSURI WATER SUPPLY SCHEME, T W NO 2 , [ AUGMENTATION ] , JJM WORKS, SCHEME CODE SM/15905, APPLICATION NO 2004809558, REFERENCE ID 204352004, DASPUR CCC, WBSEDCL. |  |  | BILL/01632/2024-2025 | C072443865657 | 29/07/2024 | 29/07/2024 | WBSEDCL | 4.59 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15905 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (998) for Augmentation of Supapursuri PWSS in Daspur-I block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000180/2023-2024 | 2720/MD | 31/07/2023 | 27/10/2025 | M/S. D.K.H.CONSTRUCTION | 127.08 | 39.8 | 31.32 | 15
7 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15905 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000017/2023-2024 | 1133/W/MMD | 12/04/2023 | 03/10/2024 | BUSR ENGINEERING | 25.25 | 12.6 | 49.88 | 100
8 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15905 | Augmentation | Laying additional distribution system pipe line to provide balance FHTC for Augmentation of Supapursuri W/S Scheme, Block - Daspur-I, Dist.- Paschim Medinipur under Midnapore Division, PHE Dte. (PART-B) | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000101/2024-2025 | 2847/MD | 09/09/2024 | 01/04/2025 | SK REAJUL HOSSAIN | 15.33 | 0 | 0 | 100
9 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15905 | Augmentation | Laying additional distribution system pipe line to provide balance FHTC for Augmentation of Supapursuri W/S Scheme, Block - Daspur-I, Dist.- Paschim Medinipur under Midnapore Division, PHE Dte. (PART-A) | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000100/2024-2025 | 2846/MD | 09/09/2024 | 08/03/2025 | M/S. D.K.H.CONSTRUCTION | 32.36 | 0 | 0 | 100
Total | [13 empty] | 229.87 | 56.6 | 24.62