## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15905 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Ghatal block under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division |  | ORD/000736/2022-2023 | 2683/MD | 30/12/2022 | 20/01/2023 | RISHAN ENGINEERING CONSULTANCY | 7.72 | 2.08 | 26.95 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15905 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Daspur-I block under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division |  | ORD/000735/2022-2023 | 2682/MD | 30/12/2022 | 20/01/2023 | RISHAN ENGINEERING CONSULTANCY | 7.76 | 2.12 | 27.25 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15905 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000138/2022-2023 | 413/MD | 07/02/2023 | 07/02/2023 | Resource Division | 6.69 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15905 | Augmentation | SUPAPURSURI WATER SUPPLY SCHEME, T W - III , JJM WORKS, SCHEME CODE SM/15905, APPLICATION NO 2004588382, REFERENCE ID 204209925, DASPUR CCC, WBSEDCL |  |  | BILL/04200/2023-2024 | BP-2023-24-787 | 06/03/2024 | 06/03/2024 | WBSEDCL | 3.08 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15905 | Augmentation | QUOTATION MONEY FOR SUPAPURSURI WATER SUPPLY SCHEME, T W NO 2 , [ AUGMENTATION ] , JJM WORKS, SCHEME CODE SM/15905, APPLICATION NO 2004809558, REFERENCE ID 204352004, DASPUR CCC, WBSEDCL. |  |  | BILL/01632/2024-2025 | C072443865657 | 29/07/2024 | 29/07/2024 | WBSEDCL | 4.59 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUPAPURSURI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE | SM/15905 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (998) for Augmentation of Supapursuri PWSS in Daspur-I block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000180/2023-2024 | 2720/MD | 31/07/2023 | 27/10/2025 | M/S. D.K.H.CONSTRUCTION | 127.08 | 39.8 | 31.32 | 15
Total | [13 empty] | 156.93 | 44 | 28.04