## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | THAUR AND ITS ADJOINING MOUZAS PWSS | SM/15906 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 1163/MD | 26/04/2023 | 26/04/2023 | Resource Division | 33.8 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | THAUR AND ITS ADJOINING MOUZAS PWSS | SM/15906 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF THAUR PWSS. REF CONSUMER ID-204342953, APPLICATION NO-2004797675, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESPUR |  |  | BILL/01471/2024-2025 | BP-2024-25-415 | 15/07/2024 | 15/07/2024 | WBSEDCL | 3.08 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | THAUR AND ITS ADJOINING MOUZAS PWSS | SM/15906 | New | Electric quotation bill for Tw No-II of Thaur PWSS. (Ref Consumer ID-204182374) |  |  | BILL/03343/2023-2024 | BP-2023-24-561 | 16/01/2024 | 16/01/2024 | WBSEDCL | 3.12 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | THAUR AND ITS ADJOINING MOUZAS PWSS | SM/15906 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THAUR AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002003/2022-2023 | 905/W/MMD | 27/03/2023 | 01/11/2025 | SUJOY RANJAN BHOWMICK | 27.37 | 18.46 | 67.45 | 25
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | THAUR AND ITS ADJOINING MOUZAS PWSS | SM/15906 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 300 Cum & 400 Cum RCC Over Head Reservoir (Intze type with Pile Foundation) & Accommodate FHTC (4,797 Nos.) including Two years O&M under JJM with allied work for Teghari & Thaur & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000224/2023-2024 | 2924/MD | 16/08/2023 | 29/05/2026 | M/S. A.R. ENTERPRISE. | 1490.96 | 138.23 | 9.27 | 49
Total | [13 empty] | 1558.33 | 156.69 | 10.06