## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-I at Mouza-Basudevpur, JL-63 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000671/2022-2023 | 750/MD | 13/03/2023 | 27/03/2023 | DEBASIS DATTA | 9.5 | 9.05 | 95.27 | 90
2 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur -II (1 no), (i)At Mouza- Dudkorma, JL-245 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000668/2022-2023 | 738/MD | 10/03/2023 | 24/03/2023 | A.R. CONSTRUCTION | 9.57 | 9.2 | 96.13 | 100
3 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed 26 nos. Mini Pipe W/S Scheme within Block Chandrakona-II (1 nos.), (i) at Mouza-Kharsa JL-231 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000667/2022-2023 | 735/MD | 10/03/2023 | 24/03/2023 | TARUN MAHATA | 9.5 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-II at Mouza-Basanchora, JL-68 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000028/2023-2024 | 968/MD | 06/04/2023 | 20/04/2023 | OM UDYUG | 9.54 | 8.8 | 92.27 | 90
5 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-I at Mouza-Paikpara, JL-267 in Paschim Medinipur District under Midnapore Division, PHE Dte. [PART-B] | AE Ghatal Sub-division |  | ORD/000029/2023-2024 | 967/MD | 06/04/2023 | 20/04/2023 | MALLIK CONSTRUCTION | 9.54 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Jote Ganashyam, JL-240 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000055/2023-2024 | 1437/MD | 04/05/2023 | 18/05/2023 | M/S. BLUE BIRD | 9.58 | 9.33 | 97.35 | 98
7 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Electric quotation bill of WBSEDCL. |  |  | BILL/00370/2023-2024 |  | 18/07/2023 | 18/07/2023 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.13 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Quotation as per WBSEDCL under Banpatna, Kankuria, Dudkomra, Nabinmanua, Jateghanashyam, Nischintapur, Jagannathur, Gochhati, Arit and Bhuta Water Supply Scheme. |  |  | BILL/00128/2023-2024 | 23-24-78-79-84 | 12/05/2023 | 12/05/2023 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 1.29 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Electric quotation bill for Ghanarampur mini PWSS Tube Well in connection Chandrakona Town CCC for payment to WBSEDCL. |  |  | BILL/00343/2023-2024 | BP-2023-24-173 | 20/07/2023 | 20/07/2023 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 1.51 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Mechanical | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Electric quotation for kankuria mini w/s.(consumer ID-203877119) |  |  | BILL/00092/2023-2024 |  | 19/04/2023 | 19/04/2023 | WBSEDCL | 0.13 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Electric Quotation Bill of Mararampur, Basudevpur & Dharma Mini |  |  | BILL/00203/2023-2024 | 23-24-128-29-30 | 19/06/2023 | 19/06/2023 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.38 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Ghanarmpur, Paikpara-I, Paikpara-II, Murakata, Basanchora, Peardanga, Karasia, Nischintapur, Gargarighat, Kharsa, Hematpur, Bala W/S Scheme. |  |  | BILL/00294/2023-2024 |  | 05/07/2023 | 05/07/2023 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 1.51 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Mechanical | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Electric quotation for Banpatna w/s mini scheme(Consumer ID-203877125) |  |  | BILL/00089/2023-2024 |  | 19/04/2023 | 19/04/2023 | WBSEDCL | 0.13 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Electric quotation bill of WBSEDCL. |  |  | BILL/00527/2023-2024 | BP-2023-24-273 | 28/08/2023 | 28/08/2023 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 0.13 | 0 | 0 | 0
15 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-I at Mouza-Dharma, JL-145 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000026/2023-2024 | 966/MD | 06/04/2023 | 20/04/2023 | OM UDYUG | 9.45 | 9.05 | 95.81 | 90
16 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-II at Mouza-Ghanarampur, JL-257 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/RWS Midnapore Sub Division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000674/2022-2023 | 784/MD | 17/03/2023 | 31/03/2023 | M/S. SUBHAS CHANDRA KUNDU | 9.18 | 8.68 | 94.53 | 100
17 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Gochhati, JL-161 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000054/2023-2024 | 1436/MD | 04/05/2023 | 18/05/2023 | M/S. BLUE BIRD | 9.58 | 9.34 | 97.46 | 98
18 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Jagannathpur, JL-85 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/RWS Midnapore Sub Division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000098/2023-2024 | 2473/MD | 14/07/2023 | 28/07/2023 | MAHAPRABHU ENTERPRISE | 9.59 | 9.32 | 97.2 | 90
19 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-II at Mouza-Murakata, JL-49 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Chandrakona-II) | ORD/000817/2023-2024 | 653/MD | 07/03/2024 | 21/03/2024 | M/S. INDRAJIT ROY | 9.53 | 0 | 0 | 0
20 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme Within Block Chandrakona-I at Mouza-Hematpur JL-209 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000666/2022-2023 | 734/MD | 10/03/2023 | 24/03/2023 | HYDRO TECH ASSOCIATES | 9.28 | 9.11 | 98.21 | 90
21 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-I at Mouza-Paikpara, JL-267 in Paschim Medinipur District under Midnapore Division, PHE Dte. [PART-A] | AE Ghatal Sub-division |  | ORD/000673/2022-2023 | 782/MD | 17/03/2023 | 31/03/2023 | PRITI ENTERPRISE | 9.32 | 9.03 | 96.89 | 90
22 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Kharagpur-I at Mouza-Kankuria, JL-281 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000726/2022-2023 | 868/MD | 28/03/2023 | 11/04/2023 | AJITESH ACHARJEE | 9.52 | 8.78 | 92.26 | 90
23 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Arit, JL-220 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000728/2022-2023 | 869/MD | 28/03/2023 | 11/04/2023 | A R ENTERPRISE | 9.59 | 9.56 | 99.69 | 90
24 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Kharagpur-I at Mouza-Banpatna, JL-340 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000727/2022-2023 | 867/MD | 28/03/2023 | 11/04/2023 | RITESH AGARWALL | 9.59 | 9.59 | 100 | 90
25 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-I at Mouza-Nischintapur, JL-264 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000729/2022-2023 | 870/MD | 28/03/2023 | 11/04/2023 | M/S. INDRAJIT ROY | 9.54 | 9.32 | 97.64 | 90
26 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Nischintapur, JL-230 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/RWS Midnapore Sub Division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000027/2023-2024 | 964/MD | 06/04/2023 | 20/04/2023 | SAJAL JANA | 9.59 | 9.55 | 99.59 | 100
27 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Bhuta, JL-187 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000675/2022-2023 | 785/MD | 17/03/2023 | 31/03/2023 | S.K. CONSTRUCTION | 9.53 | 9.52 | 99.92 | 90
28 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-II at Mouza-Karasia, JL-77 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/RWS Midnapore Sub Division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000025/2023-2024 | 965/MD | 06/04/2023 | 20/04/2023 | BENGAL TRADERS | 9.59 | 9.42 | 98.28 | 90
29 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Mechanical | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & Kharagpur-I (2 Nos.) in Paschim Medinipur District under Midnapore Division, PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001858/2022-2023 | 773/W/MMD | 23/03/2023 | 19/09/2023 | BHABANI PRASAD MANNA | 68.08 | 67.01 | 98.43 | 97
30 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-II at Mouza-Peardanga, JL-79 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/RWS Midnapore Sub Division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000134/2023-2024 | 2593/MD | 21/07/2023 | 04/08/2023 | SARADA CONSTRUCTION | 9.5 | 9.42 | 99.25 | 100
31 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Material Requisition To Resource Division |  |  | RTOR000082/2024-2025 | 3433/MD | 25/11/2024 | 25/11/2024 | Resource Division | 16.02 | 0 | 0 | 0
32 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Mechanical | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Additional Electric quotation bill of Jotekanuramgarh pwss (Ref Consumer ID-203856003),Application No-2004144274,Application Type-New Connection,Name of ccc-Daspur ccc, block-Daspur-I. |  |  | BILL/03731/2023-2024 |  | 12/02/2024 | 12/02/2024 | WBSEDCL | 0 | 0 | 0 | 0
33 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Mechanical | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Electrict quotation bill for Jotekanuramgarh pwss (Ref Consumar ID-203856003),Application No-2004144274,Application Type-New Connection,Name of ccc-Daspur ccc, block-Daspur-II. |  |  | BILL/03700/2023-2024 |  | 09/02/2024 | 09/02/2024 | WBSEDCL | 0.13 | 0 | 0 | 0
34 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed 26 nos. Mini Pipe W/S Scheme within Block Daspur -I (1 nos),(i) At Mouza-Makrampur JL no-125& in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000677/2022-2023 | 803/MD | 20/03/2023 | 03/04/2023 | S.M. ENTERPRISE | 9.3 | 0 | 0 | 100
35 | PASCHIM MEDINIPUR | Chandrakona-I,Chandrakona-II,Daspur-I,Daspur-II,Kharagpur-I | Midnapore Division | Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & | SM/16202 | New | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-II at Mouza-Bala, JL-239 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/RWS Midnapore Sub Division | JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Chandrakona-II) | ORD/000407/2023-2024 | 5133/MD | 02/11/2023 | 21/01/2025 | ADITYA ENTERPRISE | 9.43 | 0 | 0 | 100
Total | [13 empty] | 307.75 | 233.08 | 75.74