## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURSHURI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/16252 | New | Material Requisition To Resource Division |  |  | RTOR000119/2022-2023 | 1162/MD | 25/04/2023 | 25/04/2023 | Resource Division | 52.06 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Chandrakona-I | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURSHURI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/16252 | New | New service connection for Pursuri T/W-2 water supply scheme |  |  | BILL/01332/2023-2024 | 99/JMD | 23/02/2024 | 23/02/2024 | WBSEDCL | 4.69 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Chandrakona-I | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURSHURI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/16252 | New | New service connection for Pursuri T/W -1 water supply scheme. |  |  | BILL/01331/2023-2024 | 98/JMD | 23/02/2024 | 23/02/2024 | WBSEDCL | 7.84 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURSHURI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/16252 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURSHURI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000059/2023-2024 | 1231/W/MMD | 25/04/2023 | 01/03/2025 | PRADIP KUMAR DHABAL | 25.24 | 0 | 0 | 80
5 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURSHURI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/16252 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 450 cum OHR each (Intze type with pile foundation) & Accommodate FHTC (6283 Nos.) under JJM with allied work for Purshuri & Ramkrishnapur PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000075/2023-2024 | 2422/MD | 13/07/2023 | 28/09/2025 | GOBINDA MAITY | 1504.9 | 226.6 | 15.06 | 60
6 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURSHURI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. | SM/16252 | New | Laying of rising main & additional distribution pipe line due to re-design of mouzas Pipe W/S Schemes [Mangrul / Ramkrishnapur / Bagchhari / Purshuri] at Chandrakona-I block under Ghatal Sub-Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000380/2024-2025 | 55/MD | 07/01/2025 | 30/09/2025 | GOBINDA MAITY | 79.62 | 0 | 0 | 60
Total | [13 empty] | 1674.35 | 226.6 | 13.53