## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | CHAKKESHI AND ITS ADJOINING MOUZAS PWSS | SM/16259 | New | Material Requisition To Resource Division |  |  | RTOR000090/2022-2023 | 198/MD | 16/01/2023 | 16/01/2023 | Resource Division | 26.69 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | CHAKKESHI AND ITS ADJOINING MOUZAS PWSS | SM/16259 | New | Material Requisition To Resource Division |  |  | RTOR000083/2024-2025 | 3434/MD | 25/11/2024 | 25/11/2024 | Resource Division | 11.38 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | CHAKKESHI AND ITS ADJOINING MOUZAS PWSS | SM/16259 | New | Quotation for new power connection at Chak keshi PWSS P/H- II , application no - 2004609056 , Ref id - 204222612 |  |  | BILL/04188/2023-2024 | BP-2023-24-772 | 06/03/2024 | 06/03/2024 | WBSEDCL | 3.37 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | CHAKKESHI AND ITS ADJOINING MOUZAS PWSS | SM/16259 | New | Quotation for new power connection at ckakkesi PWSS , T/W - I , Application no - 2004582548 , Ref ID - 204206277 , Madpur CCC |  |  | BILL/03750/2023-2024 | BP-2023-24-707 | 16/02/2024 | 16/02/2024 | WBSEDCL | 3.51 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | CHAKKESHI AND ITS ADJOINING MOUZAS PWSS | SM/16259 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHAKKESHI AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001944/2022-2023 | 830/W/MMD | 24/03/2023 | 01/04/2025 | WEST BENGAL ENGINEERING CO. | 22.63 | 0 | 0 | 80
6 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | CHAKKESHI AND ITS ADJOINING MOUZAS PWSS | SM/16259 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, soil investigation , 200 Cum OHR (Intze type with Raft foundation) & Accommodate FHTC (1847 nos.) under JJM with allied work including 02(Two )Years Operation & Maintenance for Chakkeshi & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000127/2023-2024 | 2525/MD | 18/07/2023 | 25/06/2026 | SUJATA CONSTRUCTION | 482.35 | 169.63 | 35.17 | 75
Total | [13 empty] | 549.94 | 169.63 | 30.84