## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001968/2022-2023 | 880/W/MMD | 27/03/2023 | 23/09/2023 | ORIENTAL ENGINEERING CO. | 45.55 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | Sinking of 1 (One) No. Tube well for Rupnarayanpur & its adjoining mouzas (Zone-II) PWSS in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000119/2023-2024 | 2519/MD | 18/07/2023 | 02/08/2023 | THE TILES | 6.19 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | Material Requisition To Resource Division |  |  | RTOR000276/2023-2024 | 4049/MD | 12/10/2023 | 12/10/2023 | Resource Division | 15.84 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | Laying Distribution Pipeline & Accommodate FHTC (200 Nos.) under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-III] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000843/2023-2024 | 745/MD | 13/03/2024 | 27/04/2024 | NIMAI LAL GURIA | 40.38 | 0 | 0 | 65
5 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | Laying Rising main, Distribution Pipeline & Accommodate FHTC (206 Nos.) including 2 yrs. O&M under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000861/2023-2024 | 834/MD | 15/03/2024 | 29/04/2024 | SAI TUBE CO. | 51.27 | 0 | 0 | 65
6 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | Construction of Pump House & Accommodate FHTC (240 Nos.) under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-IV] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000862/2023-2024 | 835/MD | 15/03/2024 | 14/05/2024 | HYDROTECH ASSOCIATES | 20.6 | 0 | 0 | 60
7 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | Laying Rising main, Distribution Pipeline & Accommodate FHTC (200 Nos.) under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE Kharagpur Sub-division |  | ORD/000851/2023-2024 | 828/MD | 15/03/2024 | 29/04/2024 | PULLOCK KUMAR GHOSH | 42.81 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | Construction of 150 CuM OHR (Torch type with Solid raft) & Boundary wall under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | AE Kharagpur Sub-division |  | ORD/000860/2023-2024 | 833/MD | 15/03/2024 | 11/09/2024 | SUBRATA KUMAR BERA | 89.95 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | Laying Distribution Pipeline under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-III) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000898/2023-2024 | 836/MD | 15/03/2024 | 29/04/2024 | S.B. ENTERPRISE | 25.73 | 0 | 0 | 88
10 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | Laying Distribution Pipeline & Accommodate FHTC (241 Nos.) under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-III] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000005/2024-2025 | 1838/MD | 12/06/2024 | 27/07/2024 | DEBASISH DOGRA | 40.29 | 0 | 0 | 60
11 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | Construction of 150 CuM OHR (Torch type with Solid raft), Pump House, Boundary wall & Accommodate FHTC (200 Nos.) under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | AE Kharagpur Sub-division |  | ORD/000320/2024-2025 | 3550/MD | 04/12/2024 | 02/06/2025 | BIDYUT KUMAR SANTRA | 108.07 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | Sinking of 3 (Three) Nos. Tube well for Rupnarayanpur & its adjoining mouzas (Zone-I) PWSS in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000118/2023-2024 | 2518/MD | 18/07/2023 | 27/08/2023 | DEBASISH DOGRA | 18.02 | 0 | 0 | 90
13 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | Sinking of 3 (Three) Nos. Tube well for Rupnarayanpur & its adjoining mouzas (Zone-III) PWSS in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000120/2023-2024 | 2520/MD | 18/07/2023 | 27/08/2023 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 17.74 | 0 | 0 | 100
14 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | QUOTATION MONEY FOR RUPNARAYANPUR WATER SUPPLY SCHEME [ JINSAR ] , ZONE-III/I, T W NO I, JJM WORKS, SCHEME CODE SM/16262, APPLICATION NO 2004582814, REFERENCE ID 204206254, NIMPURA CCC, WBSEDCL |  |  | BILL/03778/2023-2024 | BP-2023-24-714 | 20/02/2024 | 20/02/2024 | WBSEDCL | 0.12 | 0 | 0 | 0
15 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | QUOTATION MONEY FOR RUPNARAYANPUR WATER SUPPLY SCHEME ( SOVANIPUR ), ZONE-III JJM WORKS, SCHEME CODE SM/16262, APPLICATION NO 2004582809, REFERENCE ID 204206252, NIMPURA CCC, WBSEDCL |  |  | BILL/03660/2023-2024 | BP-2023-24-703 | 16/02/2024 | 16/02/2024 | WBSEDCL | 0.12 | 0 | 0 | 0
16 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | RUPNARAYANPUR WATER SUPPLY SCHEME,ZONE-III, T W - I , JJM WORKS, SCHEME CODE SM/16262, APPLICATION NO 2004606325, REFERENCE ID 204221223, KHARAGPUR CCC, WBSEDCL |  |  | BILL/04201/2023-2024 | BP-2023-24-780 | 06/03/2024 | 06/03/2024 | WBSEDCL | 0.54 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | QUOTATION MONEY FOR KASHIJORA WATER SUPPLY SCHEME ( JINSAR ), MINI, ZONE-III JJM WORKS, SCHEME CODE SM/16262, APPLICATION NO 2004582814, REFERENCE ID 204206254, NIMPURA CCC, WBSEDCL |  |  | BILL/00596/2024-2025 |  | 24/04/2024 | 24/04/2024 | WBSEDCL | 0.12 | 0 | 0 | 0
18 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | RUPNARAYANPUR WATER SUPPLY SCHEME, MINI , ZONE - I , T W NO 1 , JJM WORKS, SCHEME CODE SM/16262, APPLICATION NO 2004614456, REFERENCE ID 204224878, NIMPURA CCC, WBSEDCL |  |  | BILL/04202/2023-2024 | BP-2023-24-779 | 06/03/2024 | 06/03/2024 | WBSEDCL | 0.11 | 0 | 0 | 0
19 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | QUOTATION MONEY FOR RUPNARAYANPUR [ ZONE-III/ T W NO I ] WATER SUPPLY SCHEME, MINI- JINSAHAR , JJM WORKS, SCHEME CODE 16262, APPLICATION NO 2004652971, REFERENCE ID 204253744, NIMPURA CCC, WBSEDCL |  |  | BILL/00312/2024-2025 | BP-2024-25-80 | 24/04/2024 | 24/04/2024 | WBSEDCL | 1.47 | 0 | 0 | 0
20 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte.(Part-II) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002011/2022-2023 | 881/W/MMD | 27/03/2023 | 01/09/2025 | M/S B ENTERPRISE | 17.88 | 0 | 0 | 80
21 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002724/2023-2024 | 1069/W/MMD | 14/03/2024 | 10/09/2024 | SWAPAN BANERJEE | 10.42 | 0 | 0 | 100
22 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/16262 | New | Laying Pipeline (Distribution system & Rising main), Switch Room, Land development & Accommodate FHTC (164 Nos.) under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-III) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000006/2024-2025 | 1839/MD | 12/06/2024 | 06/08/2025 | A R ENTERPRISE | 48.59 | 0 | 0 | 86
Total | [13 empty] | 601.82 | 0 | 0