## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Abasgarh mouza. | SM/16296 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation / Augmentation of existing Abasgarh PWSS within Midnapore Saar Block under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/001012/2021-2022 | 531/MD | 21/03/2022 | 31/03/2022 | GOBINDA MAITY | 2.26 | 2.14 | 94.49 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Abasgarh mouza. | SM/16296 | Augmentation | Sinking of 150 X 100 mm dia. X 150 Mtr. Depth Rig bored Tube well for boosting purpose including FHTC, Valve chamber and other ancillary works of under Augmentation of Abasgarh W/S Scheme under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000670/2022-2023 | 723/MD | 09/03/2023 | 13/04/2023 | WATER LINK | 11.31 | 6.41 | 56.66 | 50
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Abasgarh mouza. | SM/16296 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Abasgarh mouza. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002002/2022-2023 | 904/W/MMD | 27/03/2023 | 12/09/2025 | ECO ENTERPRISE | 10.78 | 6.25 | 58.03 | 40
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Abasgarh mouza. | SM/16296 | Augmentation | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW III of Abasgarh water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000110/2023-2024 | 428/MMSD-I | 24/04/2023 | 09/05/2023 | SUJOY RANJAN BHOWMICK | 4.37 | 4.37 | 100 | 100
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Abasgarh mouza. | SM/16296 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000206/2023-2024 | 1422/MD | 04/05/2023 | 04/05/2023 | Resource Division | 18.38 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Abasgarh mouza. | SM/16296 | Augmentation | QUOTATION MONEY FOR T W NO 3 OF ABASHGARH WATER SUPPLY SCHEME [ REF- CONSUMER ID 203990474, UNDER RAJABAZAR CCC, WBSEDCL ] |  |  | BILL/00156/2023-2024 | BP-2023-24-43 | 19/05/2023 | 19/05/2023 | WBSEDCL | 0.31 | 0 | 0 | 0
Total | [13 empty] | 47.4 | 19.17 | 40.45