## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | DHITPUR AND ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/16374 | New | Material Requisition To Resource Division |  |  | RTOR000085/2022-2023 | 194/MD | 16/01/2023 | 16/01/2023 | Resource Division | 21.9 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | DHITPUR AND ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/16374 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DHITPUR AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001987/2022-2023 | 837/W/MMD | 24/03/2023 | 20/09/2023 | HARA PROSAD DAS | 23.73 | 13.12 | 55.27 | 70
3 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | DHITPUR AND ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/16374 | New | Quotation for new power connection at Dhitpur water supply scheme T/W - I |  |  | BILL/03558/2023-2024 | BP-2023-24-623 | 07/02/2024 | 07/02/2024 | WBSEDCL | 1.28 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | DHITPUR AND ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/16374 | New | Quotation for new power connection at Dhitpur PWSS P/H- II , application no - 2004609048 , Ref id - 204222614 |  |  | BILL/04193/2023-2024 | BP-2023-24-776 | 06/03/2024 | 06/03/2024 | WBSEDCL | 4.62 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | DHITPUR AND ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/16374 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, soil investigation, 300 Cum OHR (Intze type with Pile foundation) & Accommodate FHTC (2432 nos.) under JJM with allied work including 02 (Two) Years Operation & Maintenance for Dhitpur & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE2 Kharagpur Sub Division | ORD/000063/2023-2024 | 2144/MD | 08/06/2023 | 25/09/2025 | M/S. EL-CON | 649.48 | 249.15 | 38.36 | 60
Total | [13 empty] | 701.02 | 262.27 | 37.41