## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | MURAKATA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16542 | New | Material Requisition To Resource Division |  |  | RTOR000128/2023-2024 | 1324/MD | 28/04/2023 | 28/04/2023 | Resource Division | 30.06 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | MURAKATA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16542 | New | Hiring of Diesel Driven Motor Cab (BS-IV & Above) hiving contract carriage permit along with driver for office of the Store & Workshop Sub Division, Central Drilling Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000210/2023-2024 | 12/S&WSD | 15/01/2024 | 31/07/2024 | SULEKHA GHOSH | 0.94 | 0.64 | 68.06 | 15
3 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | MURAKATA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16542 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MURAKATA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002291/2022-2023 | 499/W/MMD | 20/03/2023 | 01/06/2025 | PADMA ENGINEERING CO. | 32.97 | 22.68 | 68.79 | 25
4 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | MURAKATA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16542 | New | Continuation for Hiring of Diesel Driven Motor Cab (BS-IV & Above) having contract carriage permit along with driver for office of the Store & Workshop Sub Division, Central Drilling Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 157/S&WSD | 26/07/2024 | 26/01/2025 | SULEKHA GHOSH | 0.87 | 2.05 | 234.08 | 0
5 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | MURAKATA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16542 | New | Route survey & way leave permission along & across of National Highway in Murakata PWSS under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000503/2024-2025 | 586/MD | 03/03/2025 | 24/03/2025 | DONA ASSOCIATES | 8.74 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | MURAKATA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16542 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 220 Mtrs. Depth) by utilizing Departmental Machineries for Murakata W/S Scheme (T/W-I, II & III), Keshiary Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000117/2023-2024 | 1438/CDD | 26/09/2023 | 01/01/2025 | PADMA ENGINEERING & CO. | 36.93 | 20.52 | 55.56 | 35
Total | [13 empty] | 110.52 | 45.89 | 41.52