## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | MALIHATI AND IT'S ADJOINING MOUJAS PWSS | SM/16615 | New | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 1160/MD | 25/04/2023 | 25/04/2023 | Resource Division | 31.04 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | MALIHATI AND IT'S ADJOINING MOUJAS PWSS | SM/16615 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MALIHATI AND IT'S ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000078/2023-2024 | 1278/W/MMD | 04/05/2023 | 31/10/2023 | MENAKA ENTERPRISE | 22.54 | 17.39 | 77.14 | 50
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | MALIHATI AND IT'S ADJOINING MOUJAS PWSS | SM/16615 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000205/2023-2024 | 2821/MD | 07/08/2023 | 06/10/2025 | GOBINDA MAITY | 4353.07 | 151.2 | 3.47 | 25
Total | [13 empty] | 4406.65 | 168.59 | 3.83