## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Ramchandrapur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/16632 | New | Material Requisition To Resource Division |  |  | RTOR000047/2022-2023 | 106/MD | 10/01/2023 | 10/01/2023 | Resource Division | 43.22 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Ramchandrapur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/16632 | New | Material Requisition To Resource Division |  |  | RTOR000017/2024-2025 | 3338/MD | 25/11/2024 | 25/11/2024 | Resource Division | 4.95 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Ramchandrapur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/16632 | New | QUOTATION MONEY FOR RAMCHANDRAPUR WATER SUPPLY SCHEME, T W - II , JJM WORKS, SCHEME CODE SM/16632, APPLICATION NO 2004696180, REFERENCE ID 204284327, DASPUR CCC, WBSEDCL |  |  | BILL/00638/2024-2025 | BP-2024-25-116 | 06/05/2024 | 06/05/2024 | WBSEDCL | 3.18 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Ramchandrapur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/16632 | New | QUOTATION MONEY FOR RAMCHANDRAPUR WATER SUPPLY SCHEME, T W - I , JJM WORKS, SCHEME CODE SM/16632, APPLICATION NO 2004696177, REFERENCE ID 204284325, DASPUR CCC, WBSEDCL |  |  | BILL/00643/2024-2025 | BP-2024-25-115 | 06/05/2024 | 06/05/2024 | WBSEDCL | 3.19 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Ramchandrapur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/16632 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ramchandrapur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001628/2022-2023 | 537/W/MMD | 20/03/2023 | 01/04/2026 | BALAJI CONSTRUCTION | 22.79 | 0 | 0 | 80
6 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Ramchandrapur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/16632 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 150 cum OHR (Intze type with pile foundation) & Accommodate FHTC (803 nos) under JJM with allied work for Ramchandrapur PWSS in Daspur- I Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance Charge within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000062/2023-2024 | 2416/MD | 13/07/2023 | 26/12/2025 | SAI TUBE CO. | 284.53 | 76.88 | 27.02 | 80
Total | [13 empty] | 361.84 | 76.88 | 21.25