## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING OF GROUND WATER BASED BHIMPUR PWSS TO ACCOMMODATE FHTC INCLUDING ALLIED WORKS UNDER JJM UNDER SALBONI BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MIDNAPORE DIVISION,P.H.E. Dte. | SM/16949 | Retrofitting | Accommodate balance FHTC (150 Nos.) and others allied works for Ground Water Based Bhimpur PWSS under JJM of Salboni Block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000107/2023-2024 | 2489/MD | 17/07/2023 | 16/08/2023 | DIPAK KUMAR BAKLY | 13.72 | 0 | 0 | 95
2 | PASCHIM MEDINIPUR |  | Midnapore Division | RETROFITTING OF GROUND WATER BASED BHIMPUR PWSS TO ACCOMMODATE FHTC INCLUDING ALLIED WORKS UNDER JJM UNDER SALBONI BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MIDNAPORE DIVISION,P.H.E. Dte. | SM/16949 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Bhimpur, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000864/2020-2021 | 348/MD | 25/02/2021 | 07/03/2021 | SIRCON ENGINEERING SERVICES | 1.99 | 0 | 0 | 0
Total | [13 empty] | 15.71 | 0 | 0