## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONAKANIA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DANTAN- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/16999 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000141/2022-2023 | 421/MD | 08/02/2023 | 08/02/2023 | Resource Division | 3.52 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONAKANIA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DANTAN- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/16999 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONAKANIA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DANTAN- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000022/2023-2024 | 1184/W/MMD | 25/04/2023 | 22/10/2023 | AMUSAR IMPEX PVT. LTD | 23.77 | 18.83 | 79.23 | 15
3 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONAKANIA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DANTAN- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/16999 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Soil investigation, Construction of 200 cum OHR & Accommodate FHTC (125 Nos.) under JJM with allied work for Augmentation of Sonakania Pipe W/S Scheme in Dantan-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000172/2024-2025 | 3143/MD | 04/10/2024 | 29/09/2025 | SAI TUBE CO. | 156.46 | 0 | 0 | 18
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONAKANIA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DANTAN- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/16999 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Additional Tw No-II (Boosting) of SONAKANIA water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist.:- Paschim Medinipur | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002721/2023-2024 | 1066/W/MMD | 14/03/2024 | 10/09/2024 | MANORANJAN DEY | 6.72 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONAKANIA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DANTAN- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/16999 | Augmentation | Repairing of 2nd Pump House & Boundary wall for Sonakania PWSS within Dantan-I block under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000499/2024-2025 | 569/AE/HQ/MD | 28/02/2025 | 14/04/2025 | PROVAT KUMAR DE | 1.86 | 0 | 0 | 100
Total | [13 empty] | 192.32 | 18.83 | 9.79