## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF SALBANI AND IT'S ADJOINING MOUJAS PWSS, BLOCK - SALBONI, DIST.- PASCHIM MEDINIPUR. | SM/17000 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF SALBANI AND IT'S ADJOINING MOUJAS PWSS, BLOCK - SALBONI, DIST.- PASCHIM MEDINIPUR. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000036/2023-2024 | 1200/W/MMD | 25/04/2023 | 22/10/2023 | MANORANJAN DEY | 25.26 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF SALBANI AND IT'S ADJOINING MOUJAS PWSS, BLOCK - SALBONI, DIST.- PASCHIM MEDINIPUR. | SM/17000 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Soil investigation, 450 cum OHR (Intze type with solid Raft) & Accommodate FHTC (3,272 Nos.) under JJM with allied work for Augmentation of Salboni Pipe Water Supply Scheme under Salbani Block including supply of all labour & materials within Medinipur Sadar Sub-Division under Medinipur Division, PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000395/2023-2024 | 5069/MD | 26/10/2023 | 16/11/2025 | IJABUL SEKH | 552.44 | 0 | 0 | 70
3 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF SALBANI AND IT'S ADJOINING MOUJAS PWSS, BLOCK - SALBONI, DIST.- PASCHIM MEDINIPUR. | SM/17000 | Augmentation | Route survey & way leave permission along & across of National Highway in Augmentation of Salboni PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000191/2025-2026 | 1630/MD | 06/08/2025 | 27/08/2025 | PIONEER SURVEYORS | 10.84 | 0 | 0 | 0
Total | [13 empty] | 588.54 | 0 | 0