## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | AKRA MARKANDAPUR PWSS | SM/17003 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER Kharagpur - I and II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000038/2023-2024 | 1187/W/MMD | 25/04/2023 | 22/10/2023 | A G ENTERPRISE | 40.67 | 0 | 0 | 40
2 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | AKRA MARKANDAPUR PWSS | SM/17003 | New | Laying of uPVC distribution system, Rising Main, Construction of supporting structure of 10 Cum Water Tank, Switch Room cum Chlorine Room & Accommodate FHTC (124 Nos.) under JJM with allied work & 1 year O&M for Arka Markandapur Mini Water Supply Scheme in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000105/2023-2024 | 2487/MD | 17/07/2023 | 03/06/2026 | A R ENTERPRISE | 36.71 | 14.17 | 38.6 | 75
3 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | AKRA MARKANDAPUR PWSS | SM/17003 | New | Material Requisition To Resource Division |  |  | RTOR000178/2023-2024 | 1372/MD | 02/05/2023 | 02/05/2023 | Resource Division | 1.57 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | AKRA MARKANDAPUR PWSS | SM/17003 | New | Quotation for new power connection at Akramarkandapur PWSS P/H- I , application no - 2004609042 , Ref id - 204222613 |  |  | BILL/04191/2023-2024 | BP-2023-24-775 | 06/03/2024 | 06/03/2024 | WBSEDCL | 4.16 | 0 | 0 | 0
Total | [13 empty] | 83.12 | 14.17 | 17.05