## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | DAKSHIN PARSHURA AND ITS ADJOINING MOUZAS PWSS | SM/17004 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 250 Cum OHR (Intze type with Pile Foundation) & Accommodate FHTC (1,871 Nos.) including Two years O&M under JJM with allied work for Dakshin Parshura & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000232/2023-2024 | 2956/MD | 17/08/2023 | 04/02/2026 | M/S. D.K.H.CONSTRUCTION | 728.65 | 398.27 | 54.66 | 15
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | DAKSHIN PARSHURA AND ITS ADJOINING MOUZAS PWSS | SM/17004 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DAKSHIN PARSHURA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000023/2023-2024 | 1186/W/MMD | 25/04/2023 | 27/01/2025 | RSA ENTERPRISE | 22.89 | 9.97 | 43.55 | 25
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | DAKSHIN PARSHURA AND ITS ADJOINING MOUZAS PWSS | SM/17004 | New | Material Requisition To Resource Division |  |  | RTOR000051/2024-2025 | 3371/MD | 25/11/2024 | 25/11/2024 | Resource Division | 11.53 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | DAKSHIN PARSHURA AND ITS ADJOINING MOUZAS PWSS | SM/17004 | New | Electric quotation bill for Tw No-II of Daksin parshura PWSS. (Ref Consumer ID-204182381) |  |  | BILL/03340/2023-2024 | BP-2023-24-558 | 16/01/2024 | 16/01/2024 | WBSEDCL | 3.2 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | DAKSHIN PARSHURA AND ITS ADJOINING MOUZAS PWSS | SM/17004 | New | Electric quotation bill for Tw No-I of Dakshin Parshura PWSS. (Ref Consumer ID-204182272) |  |  | BILL/03339/2023-2024 | BP-2023-24-557 | 16/01/2024 | 16/01/2024 | WBSEDCL | 3.2 | 0 | 0 | 0
Total | [13 empty] | 769.46 | 408.24 | 53.06