## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION | SM/17005 | New | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Dhuipara & its adjoining Mouzas PWSS & (2) Nilda & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000762/2022-2023 | 1117/MD | 09/06/2022 | 09/07/2022 | ENVIROTECH SOLUTIONS | 4.15 | 4.15 | 100 | 100
2 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION | SM/17005 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000026/2023-2024 | 1190/W/MMD | 25/04/2023 | 31/03/2025 | RSA ENTERPRISE | 22.79 | 0.58 | 2.53 | 60
3 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION | SM/17005 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000396/2023-2024 | 5070/MD | 26/10/2023 | 25/08/2026 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 217.42 | 5.88 | 58
4 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION | SM/17005 | New | Material Requisition To Resource Division |  |  | RTOR000162/2023-2024 | 1454/MD | 08/05/2023 | 08/05/2023 | Resource Division | 30.9 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION | SM/17005 | New | Electrict quotation bill for TW-I of Dhuipara pwss (Ref Consumar ID-204310843),Application No-2004741201,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur |  |  | BILL/01071/2024-2025 | BP-2024-25-193 | 24/05/2024 | 24/05/2024 | WBSEDCL | 3.62 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION | SM/17005 | New | Electrict quotation bill for TW-II of Dhuipara pwss (Ref Consumar ID-204310840),Application No-2004741253,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur |  |  | BILL/01070/2024-2025 | BP-2024-25-194 | 24/05/2024 | 24/05/2024 | WBSEDCL | 4.55 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION | SM/17005 | New | Construction of Approach Road (3m width) of Dhuipara Piped Water Supply Scheme at Mohanpur block under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000397/2024-2025 | 153/MD | 15/01/2025 | 14/02/2025 | GOBINDA MAITY | 1.64 | 0 | 0 | 100
Total | [13 empty] | 3767.48 | 222.14 | 5.9