## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | GROUND BASED MINI PIPED WATER SUPPLY SCHEME FOR DEULBERE MOUZA, BLOCK CHANDRAKONA-II, DISTRICT-PASCHIM MEDINIPUR | SM/17008 | New | Sinking of 150 X 100 mm dia. X 165 mtr. depth deep boosting tube well by direct rotary method for Deulbere PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Ghatal Sub-division |  | ORD/000121/2023-2024 | 2521/MD | 18/07/2023 | 28/07/2023 | ANNAPURNA TUBEWELL WORKS | 6.18 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | GROUND BASED MINI PIPED WATER SUPPLY SCHEME FOR DEULBERE MOUZA, BLOCK CHANDRAKONA-II, DISTRICT-PASCHIM MEDINIPUR | SM/17008 | New | Material Requisition To Resource Division |  |  | RTOR000182/2023-2024 | 1360/MD | 02/05/2023 | 02/05/2023 | Resource Division | 0.83 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | GROUND BASED MINI PIPED WATER SUPPLY SCHEME FOR DEULBERE MOUZA, BLOCK CHANDRAKONA-II, DISTRICT-PASCHIM MEDINIPUR | SM/17008 | New | Laying distribution pipe line, Accommodate FHTC (135 Nos.) under JJM with allied work including 1 year O & M for Deulbere PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000172/2023-2024 | 2674/MD | 26/07/2023 | 09/09/2023 | SUBHASIS DOLAI | 27.2 | 0 | 0 | 90
4 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Mechanical | GROUND BASED MINI PIPED WATER SUPPLY SCHEME FOR DEULBERE MOUZA, BLOCK CHANDRAKONA-II, DISTRICT-PASCHIM MEDINIPUR | SM/17008 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER CHANDRAKONA - I and II BLOCK IN PASCHIM MIDNAPORE DISTRICTunder JJM Program under MMD PHE Dte. |  |  | ORD/000367/2023-2024 | 1693/W/MMD | 04/08/2023 | 31/01/2024 | AMUSAR IMPEX PVT. LTD | 49.92 | 0 | 0 | 80
Total | [13 empty] | 84.13 | 0 | 0