## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHAMSAI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER KESHPUR BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/17395 | Augmentation | Continuation Work Order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dhamsai, Block - Keshpur) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/001089/2021-2022 | 1113/MD | 09/07/2021 | 19/07/2021 | CIVIL FOUNDATION ENGINEERING | 1.29 | 1.23 | 95.26 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHAMSAI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER KESHPUR BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/17395 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000185/2023-2024 | 1394/MD | 03/05/2023 |  | Resource Division | 16.27 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHAMSAI TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER KESHPUR BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. | SM/17395 | Augmentation | Laying of distribution, Rising main & Accommodate balance FHTC (70 Nos.) including 2 years O & M under JJM with allied work for Augmentation of Dhamsai & its adjoining mouzas W/S scheme in Keshpur block including supply of all labour & materials within Midnapore Sadar Sub-Division under Medinipur Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000176/2023-2024 | 2716/MD | 31/07/2023 | 29/09/2023 | M/S. D.K.H.CONSTRUCTION | 118.46 | 0 | 0 | 0
Total | [13 empty] | 136.03 | 1.23 | 0.91