## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Borai Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17398 | New | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Borai & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000759/2022-2023 | 1114/MD | 09/06/2022 | 29/06/2022 | ENVIROTECH SOLUTIONS | 0.57 | 0.57 | 100 | 100
2 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Borai Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17398 | New | Material Requisition To Resource Division |  |  | RTOR000256/2023-2024 | 2007/MD | 16/05/2023 | 16/05/2023 | Resource Division | 55.28 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Borai Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17398 | New | Material Requisition To Resource Division |  |  | RTOR000213/2023-2024 | 1465 | 08/05/2023 | 08/05/2023 | Resource Division | 37.96 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | Borai Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17398 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Borai Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000025/2023-2024 | 1189/W/MMD | 25/04/2023 | 22/10/2023 | RSA ENTERPRISE | 23.01 | 0 | 0 | 0
Total | [13 empty] | 116.82 | 0.57 | 0.49