## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Dubrajpur & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. | SM/17558 | New | Material Requisition To Resource Division |  |  | RTOR000243/2023-2024 | 1530/MD | 12/05/2023 | 12/05/2023 | Resource Division | 36.37 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Dubrajpur & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. | SM/17558 | New | Electrict quotation bill for TW-I of Dubrajpur pwss (Ref Consumar ID-204373188),Application No-2004849368,Application Type-New Connection,Name of ccc-Daspur ccc, block-Daspue-II |  |  | BILL/02012/2024-2025 | C082430177901 | 20/08/2024 | 20/08/2024 | WBSEDCL | 15.54 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Dubrajpur & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. | SM/17558 | New | Electrict quotation bill for TW-II of Dubrajpur pwss (Ref Consumar ID-204362492),Application No-2004829564,Application Type-New Connection,Name of ccc-Daspur ccc, block-Daspur-II. |  |  | BILL/01806/2024-2025 | BP-2024-25-527 | 06/08/2024 | 06/08/2024 | WBSEDCL | 4.42 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Dubrajpur & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. | SM/17558 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Dubrajpur and its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000037/2023-2024 | 1202/W/MMD | 25/04/2023 | 04/04/2026 | TAPAN KUMAR SARKAR | 23.77 | 0 | 0 | 45
5 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Dubrajpur & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. | SM/17558 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1,304 Nos.) under JJM with allied work including 02 (Two) Years Operation & Maintenance for Dubrajpur & its adjoining mouzas W/S scheme in Daspur- II Block including supply of all labour & materials within Midnapore Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000261/2023-2024 | 3235/MD | 11/09/2023 | 22/07/2026 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 399.53 | 0 | 0 | 10
6 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Dubrajpur & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. | SM/17558 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 05/01/2025 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
Total | [13 empty] | 485.94 | 0 | 0