## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17559 | New | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Jarisai & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000760/2022-2023 | 1115/MD | 09/06/2022 | 29/06/2022 | ENVIROTECH SOLUTIONS | 1.61 | 1.61 | 100 | 100
2 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17559 | New | Material Requisition To Resource Division |  |  | RTOR000257/2023-2024 | 2005/MD | 16/05/2023 | 16/05/2023 | Resource Division | 34.25 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17559 | New | Material Requisition To Resource Division |  |  | RTOR000211/2023-2024 | 1463 | 08/05/2023 | 08/05/2023 | Resource Division | 9.68 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17559 | New | Electrict quotation bill for TW-I of Jarisai pwss (Zone-I) (Ref Consumar ID-204310834),Application No-2004741317,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur. |  |  | BILL/01064/2024-2025 | BP-2024-25-201 | 24/05/2024 | 24/05/2024 | WBSEDCL | 4.08 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17559 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000027/2023-2024 | 1191/W/MMD | 25/04/2023 | 06/04/2025 | GOENKA ENTERPRISE | 22.63 | 17.25 | 76.22 | 50
6 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17559 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 200 Cum & 300 Cum OHR (Intze type with Solid raft/ Pile Foundation) & Accommodate FHTC (6,605 Nos.) including Two years O&M under JJM with allied work for Jarisai PWSS (Zone-I & Zone-II) & Kashida (Zone-I & Zone-II) with in Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000466/2023-2024 | 5360/MD | 30/11/2023 | 03/10/2025 | GOBINDA MAITY | 2125.38 | 225.39 | 10.6 | 46
7 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17559 | New | Construction of Approach Road (3m width) of Jarisai (Zone-I) Piped Water Supply Scheme at Mohanpur block under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000400/2024-2025 | 156/MD | 15/01/2025 | 14/02/2025 | GOBINDA MAITY | 1.64 | 0 | 0 | 100
Total | [13 empty] | 2199.26 | 244.25 | 11.11