## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17561 | New | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kashida & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000758/2022-2023 | 1113/MD | 09/06/2022 | 29/06/2022 | ENVIROTECH SOLUTIONS | 1.69 | 1.69 | 100 | 100
2 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17561 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000029/2023-2024 | 1193/W/MMD | 25/04/2023 | 10/04/2025 | GOENKA ENTERPRISE | 22.63 | 17.25 | 76.22 | 50
3 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17561 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 200 Cum & 300 Cum OHR (Intze type with Solid raft/ Pile Foundation) & Accommodate FHTC (6,605 Nos.) including Two years O&M under JJM with allied work for Jarisai PWSS (Zone-I & Zone-II) & Kashida (Zone-I & Zone-II) with in Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000466/2023-2024 | 5360/MD | 30/11/2023 | 03/10/2025 | GOBINDA MAITY | 2125.38 | 203.53 | 9.58 | 46
4 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17561 | New | Material Requisition To Resource Division |  |  | RTOR000261/2023-2024 | 2010/MD | 16/05/2023 | 16/05/2023 | Resource Division | 24.75 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17561 | New | Material Requisition To Resource Division |  |  | RTOR000209/2023-2024 | 000209 | 08/05/2023 | 08/05/2023 | Resource Division | 24.75 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17561 | New | Material Requisition To Resource Division |  |  | RTOR000245/2023-2024 | 1532/MD | 12/05/2023 | 12/05/2023 | Resource Division | 0.67 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17561 | New | Electrict quotation bill for TW-II of Kashida pwss (Zone-II) (Ref Consumar ID-204434298),Application No-2004944507,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur |  |  | BILL/03025/2024-2025 | C112429747814 | 25/11/2024 | 25/11/2024 | WBSEDCL | 3.97 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17561 | New | Construction of Approach Road (3m width) of Kashida (Zone-I) Piped Water Supply Scheme at Mohanpur block under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000398/2024-2025 | 154/MD | 15/01/2025 | 14/02/2025 | GOBINDA MAITY | 1.97 | 0 | 0 | 100
9 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. | SM/17561 | New | Electrict quotation bill for TW-I of Kashida pwss (Zone-I) (Ref Consumar ID-204478655),Application No-2005015777,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur |  |  | BILL/03869/2024-2025 | C012539101479 | 21/01/2025 | 21/01/2025 | WBSEDCL | 4.37 | 0 | 0 | 0
Total | [13 empty] | 2210.17 | 222.46 | 10.07